## Slide 1
ECM PARTNER ENABLEMENT · PHASE 1
Running the Model by Hand
For triage leads, the shared pool and squad leads — how the tiered enablement model
operates from Day 1 with no tooling, and what we must measure while it runs
PHASE 1
Manual · one quarter
WHO RUNS IT
Triage leads + a shared pool of 4–6
WHAT IS BUILT
Nothing — a Triage Guide only
OUTCOME
Evidence for the Phase 2 decision
ECM Partner Enablement · Draft for review

## Slide 2
1
Why we are doing this by hand first
Two causes, and a sequencing argument
Context
Capacity required = concurrent intakes × a fixed engineering depth applied to every intake
CAUSE 1
The data deficit
The requirement for a data point is discovered a step at a time, after the intake has landed
Each discovery costs days of elapsed time and a small, thinly spread effort
Squads' estimate: 30–40% of total elapsed time
Tier-independent — it costs the same in any model
The most draining work the squads do
CAUSE 2
Uniform allocation
Engagement depth does not vary with how much novel design an intake needs
Of 38 scenarios: 8 need no design, 14 need a judgement, 14 need a pod, 2 are campaigns
All 38 receive the same dedicated team
Without an objective rule, depth is allocated by influence
Fixing it needs a tiering rubric, not a tool
TWO WAYS TO ADOPT THE MODEL — AND WHY WE ARE TAKING THE SECOND
Build first
Prove first (what we are doing)
Sequence
Four sprints of engineering, then run the model on the platform
One quarter of process change, then build what the evidence says to build
Business case rests on
Design assumptions
Measured results from live intakes
The baseline
Does not exist, and the build does not produce it
Produced as a by-product of running
If the model is wrong
An engineering investment is stranded
A quarter of process change, nothing stranded
The Phase 2 backlog
A designed guess at what to automate
An evidence-led list of where the effort actually went
The sequencing argument in one line: every number in the business case for a platform — the distribution, the effort baseline, the elapsed-time baseline, the size of the clerical load — does not currently exist, and running the model by hand for a quarter produces all of them.
Notes: Set the frame. This audience will deliver Phase 1, so they need to understand why the sequencing is this way round rather than just being handed a process. The equation: both terms outside our control, so headcount is the only lever. It is an allocation problem, not a throughput problem. Cause 1 is the one this room lives with. Thirty to forty per cent of elapsed time on chasing information that was never captured at intake. Note the fourth bullet — it is tier-independent, which means no amount of re-tiering fixes it. That is why the triage conversation change matters as much as the tiering does. Cause 2: all thirty-eight scenarios get the same team. The fourth bullet is uncomfortable but worth saying out loud — in the absence of an objective rule, depth gets allocated by influence. The rubric exists to replace that, and it is why tier assignment has to sit with you rather than with the partner. The table is the sequencing argument. We could build first. The problem is the business case would rest entirely on assumptions — we have no baseline, we do not know what proportion of real demand would route lighter, we do not know whether partners will accept an assigned tier. Running first answers all of that for the price of a process change. And if the model turns out to be wrong, we find out having spent a quarter rather than four sprints of engineering.

## Slide 3
2
Every platform mechanism has a human equivalent
This is the substitution table — and the right-hand column is the Phase 2 backlog in draft
What manual means
Platform mechanism (Phase 2)
Manual equivalent (Phase 1)
What is lost
Intake copilot
Structured triage conversation from a written question guide
Partner cannot self-serve; needs a skilled lead and real time
Intake data catalogue / why-register
The same content, as a written guide
Nothing material — the knowledge is the asset either way
Completeness validation
The lead scores against the published bands
Consistency depends on the lead; no automatic block
Gap register
A gaps table on the intake record
No automatic ageing or chasing
Handoff contract
A one-page Triage Outcome Record
Produced by hand, so quality varies
Tiering assistant
The lead scores seven determinants on a sheet
Takes time and varies between leads until calibrated
Pattern matcher
The lead's recall, supported by a pattern log
Weak for leads new to the domain
Scope derivation
A scope checklist per pattern in the guide
No automatic team notification
Gate engine
A gate checklist walked by lead and pool
Gates can be waived under pressure — the central risk
Partner cockpit
One shared tracker, maintained by hand
No live state for the partner; they still have to ask
Artefact generation
Templates the onboarding resource fills in
The clerical load remains almost entirely
Clinic triage
The pool's channel plus published office hours
Works well — a human process by design
Pattern catalogue
A pattern log: one page after each Dedicated delivery
Not executable; informs judgement rather than driving provisioning
Drift detector
Fortnightly review against the trigger list
Detection delayed by up to two weeks
Read the right-hand column as the Phase 2 specification in draft. What the manual approach cannot do is a more honest basis for deciding what to build than any design exercise, because it comes from running the model rather than from imagining it. Keep a note of which of these hurt most — that note is the week-12 evidence.
Notes: This is the slide that makes "manual" concrete. Walk it, but do not read every row — pick four. Row 1: the intake copilot becomes a structured conversation. We lose partner self-service and it costs real time, but we keep the substance. Row 2 is worth pointing at: the data catalogue and the why-register are the same asset in both phases. Written once, used immediately, reused unchanged. This is not throwaway work. The gate engine row is the one to flag as a risk. A written rule applied by a person under schedule pressure is weaker than a gate that blocks. That is the central discipline risk of Phase 1 and we will come back to it. The artefact generation row is where most of the clerical load sits, and it is almost entirely unaddressed by Phase 1. Be honest about that — it is the single biggest thing Phase 2 buys after Lean. THE INSTRUCTION TO THE ROOM Keep a running note of which losses in the right-hand column actually hurt in practice. Some will turn out to be irrelevant; others will be the thing that breaks a week. That note, compiled at week twelve, is a better platform backlog than anything we could design in advance.

## Slide 4
3
The Triage Guide
The only thing that gets written — and the one week it takes
Preparation
EIGHT SECTIONS
The tier model
Lean, Lean+, Dedicated and Factory — a page each. What ECM provides, what the partner owns, what the engagement feels like.
The seven determinants
D1 to D7 with the 0–3 scoring descriptors. Pattern precedent, trust posture, regulatory impact, classification engine change, data model, volume, breadth.
Thresholds and overrides
0–5 Lean, 6–11 Lean+, 12–21 Dedicated. Plus the hard overrides that force a tier regardless of score.
The question set
Fifty-four data points by category, each with why it is required, what it blocks, what a good answer looks like, and diagnostic sub-questions.
Completeness bands
Which items must be answered to accept the intake; which may be dated gaps against the design, provision and certify gates.
Guardrails by tier
The universal invariants and the tier-specific rules, written as things the lead applies and records.
Escalation triggers
The conditions that re-tier an intake, and who the lead notifies.
Templates
Triage Outcome Record · gaps table · scoring sheet · pattern log page.
EFFORT: ROUGHLY ONE WEEK OF TWO EXPERIENCED ENGINEERS PLUS A GOVERNANCE ANALYST
Drawing on what they already know. The question set with its reasons is the bulk of it — and it is the same asset the platform would have needed, written once, used immediately, and reused unchanged in Phase 2.
THE QUESTION SET IS THE BULK OF IT — 54 DATA POINTS ACROSS 10 CATEGORIES
A
5
Business context
B
6
Application & zone
C
8
Document inventory
D
5
Trust & classification
E
6
Retention & regulatory
F
7
Channel & integration
G
5
Metadata & retrieval
H
4
Security & users
I
4
Environments & cutover
J
4
Support & ownership
Each entry carries the question in partner language, why it is required, what it blocks named as a specific gate, what a good answer looks like, diagnostic sub-questions for a partner who does not know, and which patterns make it applicable — so irrelevant questions are never asked.
Notes: This is what we write before anything else happens. Be precise about the scope: it is guidance, not a system. Someone will say we were told to build nothing and here is a document. The answer: writing guidance is days of work by people who already hold the knowledge. Building a platform is months of engineering. We are doing the first and none of the second. The question set is the bulk of the effort and the most valuable part. Fifty-four points across ten categories, derived by walking the lifecycle backwards from every gate and asking what that gate needs and where it comes from. The critical field in each entry is the "why". Not "what are the document traits" but "do any of these contain handwritten annotations or signatures — this decides whether they need human review after classification, which typically adds two to three weeks and a separate engagement." A partner who understands what an answer is for gives a usable one. The second most important field is the diagnostic sub-questions. Most intake fields are blank not because the partner is unwilling but because they do not know and have no idea how to find out. Sub-questions a non-specialist can answer turn that from a dead end into a path. And applicability matters as much as coverage. The current workbook asks everyone everything, which trains people to skim. We ask only what applies to the pattern in front of us.

## Slide 5
4
The deeper triage conversation
Where most of the Phase 1 benefit comes from — a change of purpose, not just of length
The new triage
TWO SESSIONS, NOT ONE
BEFORE
Pre-read issued
The partner receives the list of what will be asked and why, so they arrive able to answer rather than discovering the questions live
>
SESSION 1 · 90 MIN
Discovery Triage
With the partner. The lead works the question guide, explains the reason at the point of asking, probes vague answers and registers every unknown
>
SESSION 2 · 30 MIN
Tiering Review
Internal. Score the seven determinants, apply overrides, assign the tier, select the guardrails, record the justification
>
AFTER
Outcome Record issued
To the partner and the delivering team: answers, gaps with owners and dates, derived scope, tier and reasoning, long-lead items to start now
WHAT THE LEAD DOES DIFFERENTLY — FOUR BEHAVIOURS
Explains the why at the point of asking
Not "what are the document traits" but "do any of these contain handwritten annotations or signatures — this decides whether they need human review, which adds two to three weeks and a separate engagement"
Treats "I don't know" as a normal state
Offers realistic options with consequences. Asks diagnostic sub-questions a non-specialist can answer. Where the answer needs someone else, registers a dated gap with a named owner.
Surfaces contradictions immediately
Rather than recording both answers and letting the conflict surface during build.
Flags long-lead items on the day
Connectivity, certificates, governance determinations and specialist engagements identified at triage and started immediately.
ONE PAGE, ISSUED EVERY TIME
The Triage Outcome Record
Answers — every applicable point, recorded
Gaps — each with named owner, due date, blocking gate
Completeness by band — accept / design / provision / certify
Derived scope — workstreams and specialist teams to engage
Long-lead items — flagged to start now
Pattern matched, or 'novel'
Tier assigned, with the determinant scores and reasoning
Guardrails in force for this intake
THE CHANGE THAT CARRIES MOST OF THE PHASE 1 BENEFIT
Today the requirement for a data point is discovered a step at a time, by an engineer, after the intake has landed — and each discovery costs days of waiting. In Phase 1 the full requirement is established in one ninety-minute conversation, with the reasons explained, and everything not yet knowable becomes a dated, owned item. Nothing is automated. The cycle is removed by asking the questions earlier and better, in one place, by someone who knows why each one matters.
Notes: This is the most important slide for the triage leads, because it is the change to their own working week. The shape change: two sessions, not one. And a pre-read, which costs almost nothing and changes the quality of the first session substantially — the partner arrives able to answer rather than discovering the questions live. Ninety minutes is deliberate. Today triage is typically forty-five and it classifies and routes. We are changing the purpose: it becomes the session where the full requirement is established. That is why it needs the time. The four behaviours — spend time on the first two. The "why at the point of asking" example is worth reading out verbatim. Notice what changes: the partner is not being asked to understand the platform, they are being told the consequence of their answer. That is a question an application team can answer well. The "I don't know" behaviour is the one that eliminates the discovery cycle. Converting "I need to ask someone" into a registered, dated, owned, gate-linked item means the question still gets answered — but it is asked once, early, by the partner's own team, against a known deadline, instead of by us, late, under pressure. THE OUTCOME RECORD One page, issued every time, to the partner and to whoever will deliver it. This is the interface. Whatever else changes, the record is what the delivering engineer reads instead of working out what is missing themselves. If a triage produces no Outcome Record, it did not happen. Make that a hard rule from week one — it is the main defence against the session quietly reverting to forty-five minutes under schedule pressure.

## Slide 6
5
Tier assignment: the lead decides
Seven determinants, three thresholds, five hard overrides — and calibration is not optional
Tiering
THE SEVEN DETERMINANTS, SCORED 0–3 ON THE SHEET
Determinant
Score 0
Score 1
Score 2
Score 3
D1
Pattern precedent
Exact repeat of a known shape
Known shape, minor variation
Partially comparable
No precedent
D2
Content trust posture
Unchanged, determined
New content, same posture
New posture for partner
Posture changing on live content
D3
Regulatory and records
None
Existing retention reused
New non-regulated retention
New regulated retention or WORM
D4
Classification engine
None
Shadow or dry run only
Engine change, no new types
Engine change with new types
D5
Data model and metadata
No change
Additive, forward only
Structural, forward only
Historical content affected
D6
Volume and performance
Within current band
Band change, below threshold
Load testing triggered
Migration-scale or peak redesign
D7
Breadth of impact
Single partner, single flow
Single partner, many flows
Multiple business units
Multiple partners or dual-target
THRESHOLDS
0 – 5
Lean
6 – 11
Lean+
12 – 21
Dedicated
HARD OVERRIDES — FORCE A TIER REGARDLESS OF SCORE
Condition
Forces
No precedent at all for this shape
Dedicated
Existing content or metadata remediated
Dedicated
New regulated retention or WORM
Dedicated
Multiple LOBs or multiple partners
Dedicated
Partner not yet through one prior intake
Not Lean
CALIBRATION IS NOT OPTIONAL — TWO LEADS WILL SCORE THE SAME INTAKE DIFFERENTLY AT FIRST
BEFORE WE START
Two half-day sessions. The leads score the same three historical intakes independently, then compare and reconcile.
FIRST TWO MONTHS
A fortnightly calibration review. Every tier assignment of the period is reviewed as a group, and divergences are discussed rather than corrected quietly.
EVERY DEVIATION
A lead may deviate from the threshold, but must record why. A determinant repeatedly overridden in the same direction is a rubric defect, not a discipline problem.
APPEAL
One appeal per intake, to the enablement lead, within five working days, naming the determinant believed to be wrongly scored.
The lead also selects which guardrails apply to the intake and records them on the Outcome Record, so the delivering team and the partner both know which rules are in force. Every waiver is recorded with the name of who authorised it, and waivers are reviewed in the fortnightly session.
Notes: This is the mechanical heart of what the leads will do, and they will stress-test it. Invite that. Seven determinants, scored zero to three on a sheet during the thirty-minute Tiering Review. The scoring descriptors are in the guide; the sheet is one page. Note what is deliberately absent from the determinants: partner size, partner seniority, who asked loudest. Those are what allocate depth today in the absence of an objective rule. D1 is the primary determinant and it is also the one that moves over time. As we build up the pattern log, intakes that scored two or three on D1 start scoring zero or one, and the distribution shifts without any other change. The hard overrides exist because the score is a proxy for risk, and in these five cases we know the risk directly. CALIBRATION — do not skip this in the room Two leads will score the same intake differently. That is expected and it is manageable, but only if we address it deliberately rather than hoping it settles. Two half-days before we start. Fortnightly reviews for the first two months, where we look at every assignment as a group. And every deviation from the threshold recorded with a reason. That last point matters: if the same determinant keeps getting overridden in the same direction, the rubric is wrong on that dimension and we recalibrate it. We are not asking people to apply a rule they think is wrong — we are asking them to record when they think it is wrong, so we can fix it. THE APPEAL One per intake, five days, must name the determinant. Repeated successful appeals on one determinant is a rubric defect, not partners gaming us.

## Slide 7
6
The shared pool
Four to six people from the existing squads — no new headcount
The pool
COMPOSITION
2
Permanent core
Continuity, pattern memory and consistent checkpoint quality. Without a core the pool has no institutional knowledge.
2–4
Rotating members
Fixed-term secondment of six to eight weeks from the three squads. Spreads the model's knowledge, avoids permanently removing anyone from delivery, and makes the move politically straightforward.
4–6
Total at any time
Sized against aggregate checkpoint load, not partner count — which is what makes it affordable.
OPERATING RHYTHM
Element
Design
Lean+ checkpoints
Two mandatory reviews per intake — design baseline and pre-promotion readiness. Booked in advance against the intake's plan. The partner brings a completed artefact; no artefact, no review, rebook.
Office hours
Fixed published slots each week, bookable by any Lean or Lean+ partner, first come first served. Unbooked time reverts to pattern log work.
Escalation duty
One pool member per week holds duty for blocked partners and failed gates, with a one-working-day response commitment.
Named guide
Each Lean+ intake gets a guide for its duration — a point of contact, not a delivery resource, carrying several intakes concurrently.
Fortnightly drift review
The pool reviews every active intake against the escalation trigger list. This replaces automated drift detection, at the cost of up to two weeks of delay.
Pattern log
After each Dedicated delivery, one page: what was built, the configuration, what varied, what was difficult, how long each phase took.
THE POOL MUST BE PROTECTED, AND IT WILL BE TESTED
The pool is drawn from delivery squads, which means every squad lead will — reasonably, and under genuine pressure — want their person back for a sprint. The first time that happens and is allowed, the pool becomes a notional construct and Lean+ quietly reverts to unsupported self-service. Protection has to be an explicit management commitment with a named escalation route, agreed before Phase 1 starts rather than negotiated when the pressure arrives.
The guide is a contact, not a resource. A guide who starts doing the partner's implementation has converted a Lean+ intake into an unfunded Dedicated one — it happens with the best intentions and it is the most likely way the pool runs out of capacity.
Notes: The pool is the second structural move and the one that costs nothing in headcount. Composition: a permanent core of two plus rotating secondments. The core matters — without it the pool has no memory and checkpoint quality varies with whoever is in the seat that month. The rotation matters too: it spreads the model's knowledge across the squads and means nobody is permanently removed from delivery, which makes the whole thing far easier to agree. Six to eight week rotations. Fixed in advance, so returns are scheduled rather than negotiated. The sizing logic is worth stating: the pool is sized against aggregate checkpoint load, not partner count. Two mandatory reviews per Lean+ intake plus escalation duty plus office hours is a calculable weekly demand. Adding a partner adds two reviews, not a team. That is exactly why Lean+ scales where Dedicated does not. ON THE RHYTHM The "no artefact, no review" rule is important and will feel harsh the first time. But a review without the artefact becomes an unplanned working session, and that is how Lean+ silently becomes Dedicated using capacity nobody allocated. THE PROTECTION POINT — do not soften this Every squad lead in this room will at some point want their person back for a sprint, and they will have a good reason. We need the protection agreed now, with a named escalation route, rather than negotiated in week six when the pressure arrives. And the guide-is-a-contact point: a guide who starts doing the partner's implementation has converted a Lean+ intake into an unfunded Dedicated one. It happens with the best intentions. Track guide time per intake and cap it.

## Slide 8
7
What we can actually reach by hand
Lean+ works well. Lean largely does not. Say so.
The ceiling
SCENARIO DISTRIBUTION — WHAT EACH APPROACH REACHES
Today
All 38 Dedicated
Phase 1 — manual
Lean 5
Lean+ 17
Dedicated 14
2
Phase 2 — at entry
Lean 8
Lean+ 14
Dedicated 14
2
Phase 2 — steady
Lean 16
Lean+ 13
Ded 7
2
A HUMAN PROCESS ALREADY
Why Lean+ works by hand
Lean+ is a human process by design — scheduled design assurance from a shared pool. Everything it depends on can be done by people with a calendar: two booked reviews, a named contact, office hours, a fortnightly drift check.
The manual version is close to the full version.
IT DEPENDS ON TOOLING
Why Lean largely does not
Lean assumes the partner can self-serve: instantiate a pattern, provision within policy bounds, clear automated gates, see their own state. Without a platform they can do none of those — they still raise requests through existing channels and still have to ask where things stand.
Manual Lean is a reduced form, viable only for the very simplest scenarios.
ELEVEN SCENARIOS SIT IN THAT GAP
Five scenarios reachable by hand against sixteen at platform steady state. That difference is the clearest single statement of what Phase 2 actually buys — and it is a specific, countable claim rather than a design argument.
Phase 1 reallocates depth; it does not remove work. The clerical load — artefacts authored by hand, routing from memory, trackers maintained manually, status answered by a person — remains almost entirely. Saying so now is what stops a successful Phase 1 becoming an argument against Phase 2 later.
Notes: This is the honesty slide and it is the one that keeps us credible. Do not let anyone leave the room thinking Phase 1 gets us most of the way. Look at what moves between the manual bar and the platform bars. Lean+ is actually HIGHER in Phase 1 — seventeen against fourteen — because scenarios that would eventually be Lean sit in Lean+ for now. Lean is dramatically lower: five against sixteen at steady state. The explanation is the two cards. Lean+ is a human process by design, so people with a calendar can do all of it. Lean assumes the partner can self-serve, and without a platform they simply cannot — they still raise requests through existing channels, still wait for human action, still have to ask where things stand. So manual Lean is a reduced form: no allocated capacity, a written runbook, office-hours support. Only viable for the very simplest scenarios — subscription extensions, notification-only, existing UI profiles, access grants, test-only support. ELEVEN SCENARIOS IN THE GAP That is the number to remember. It is a specific countable claim about what the platform buys, and it is far more persuasive than any design argument. THE THING THAT STOPS PHASE 1 EATING PHASE 2 A Phase 1 that goes well can become an argument against building — the problem looks solved and the appetite fades. Guard against that by measuring the residual, not only the improvement: how much manual effort remains, and what happens to it as volume grows. Record where it hurts. That record is the Phase 2 case.

## Slide 9
8
The tracker and the pattern log
Two hand-maintained records — and the tracker is the primary output of Phase 1
Measurement
THE TRACKER — ONE ROW PER INTAKE, IN A SPREADSHEET OR AN EXISTING BOARD
Column group
Fields
Identity
Intake reference · partner · business application · date raised
Tiering
Determinant scores D1–D7 · total · overrides applied · assigned tier · deviation reason if any
Pattern
Pattern matched from the log, or 'novel'
Completeness
Items answered · items registered as gaps · completeness by band
Gaps
Each open item with named owner, due date and the gate it blocks
Gates
P0 to P5 status and the date each was cleared
Measurement
Clarification cycles counted · stage entry and exit dates · effort by team
Escalation
Triggers fired · re-tier events and dates
THE MEASUREMENT COLUMNS ARE NOT ADMINISTRATIVE OVERHEAD
They are the primary output of Phase 1 and the reason the Phase 2 business case becomes defensible. One named owner, reviewed weekly. If the tracker is allowed to decay, Phase 1 produces a process change with no evidence behind it — which is the worst possible outcome, because it means repeating the quarter.
THE PATTERN LOG — ONE PAGE PER DELIVERED PATTERN, WRITTEN AT CLOSURE
What the partner needed
In their terms, briefly
What was configured
The actual platform configuration produced
What varied
Which parameters differed from the last comparable intake
What proved difficult
Where the time went and what surprised us
How long each phase took
Feeds the baseline
The pattern log is the manual seed of the pattern catalogue. It is not executable and cannot drive provisioning, but it does two things immediately: it lets a triage lead recognise a repeat, and it gives Phase 2 a starting set of real patterns to harden rather than a blank catalogue.
Notes: Two records. Neither is a system. Both are maintained by hand, and that is deliberate. THE TRACKER A spreadsheet or an existing board is sufficient. The columns matter more than the tool. Point hard at the measurement group. Clarification cycles counted, stage entry and exit dates, effort by team. These are the columns that will feel like overhead in week five when everyone is busy, and they are the entire reason Phase 1 is worth running. If the tracker decays, we reach week twelve with a process change and no evidence — which means we either repeat the quarter or go into the Phase 2 conversation with nothing but assertion. That is the worst outcome available to us, worse than Phase 1 going badly, because at least a bad result is a result. One named owner. Reviewed weekly. Not everyone's job. THE PATTERN LOG One page at closure. Resist the urge to template it heavily — a shared heading structure is enough, and anything more becomes a reason not to write it. Two immediate benefits: a triage lead can recognise a repeat, which improves D1 scoring over the quarter. And it gives Phase 2 a starting set of real patterns to harden rather than a blank catalogue, which is worth weeks of platform engineering time.

## Slide 10
9
Guardrails under a manual regime
A written rule applied by a person is weaker than a gate that blocks — plan for that
Guardrails
THE INVARIANTS — IDENTICAL IN EVERY TIER, NO EXCEPTIONS
Classification determination
Retention approval
Security and access review
Volume certification
Promotion ladder
Support acceptance
Audit trail
New document type re-review
HOW EACH IS ENFORCED IN PHASE 1 VERSUS PHASE 2
Guardrail
Phase 1 — enforced by a person
Phase 2 — enforced by the platform
Classification determination
The lead confirms it is registered before accepting the intake
The gate engine blocks P1 exit; provisioning refuses without it
Retention approval
The lead checks RM approval before provisioning is requested
Gate engine blocks P2 exit; never a self-service action
Security and access routing
The guide applies the published routing rules from the guide
The platform resolves routing and refuses rather than guessing
Promotion ladder
The pool walks the gate checklist before each promotion
Promotion is a platform action, never a human one
New document type
Caught at the fortnightly drift review — up to two weeks late
Detected automatically; forces escalation immediately
Audit trail
Recorded on the Outcome Record and the tracker, by hand
Written at the point of action; not reconstructable afterwards
THE CENTRAL DISCIPLINE RISK OF PHASE 1
A written rule applied by a person under schedule pressure is weaker than a gate that blocks. Guardrails will be waived — for an important partner, in a tight week, with a good reason. The defence is not to pretend otherwise: every waiver is recorded on the Outcome Record with the name of who authorised it, and every waiver is reviewed in the fortnightly session. A waiver that is visible is manageable; one that is informal is not.
GUARDRAILS ON PHASE 1 ITSELF — WATCH THESE WEEKLY
Deep triage shortened
The Outcome Record is a precondition of acceptance — a shortened triage produces a visibly incomplete record
Pool reclaimed by squads
Explicit commitment agreed before start, named escalation route, rotation terms fixed in advance
Tracker decays
One named owner, reviewed weekly — it is the primary output, not admin
Manual Lean attempted too widely
Restrict Lean to the simplest scenarios only; a partner in Lean without tooling becomes the first failure story
Notes: The invariants are identical in every tier. No tier confers an exemption, and that is what lets us defend the lighter tiers to risk and audit. The comparison table is worth walking, because it shows exactly where Phase 1 is weaker and by how much. Look at the "new document type" row. In Phase 2 it is detected automatically and forces escalation immediately. In Phase 1 we catch it at the fortnightly drift review, which means up to two weeks late. That is a real degradation and we should be honest that it exists. THE DISCIPLINE RISK — say this plainly Guardrails will be waived. For an important partner, in a tight week, with a reason that sounds good at the time. Pretending otherwise is how controls become theatre. The defence is visibility, not prohibition. Every waiver recorded on the Outcome Record with the name of who authorised it. Every waiver reviewed fortnightly. A waiver that is visible is manageable — we can see the pattern, challenge it, and decide whether the rule is wrong. An informal one teaches everyone the controls are advisory. THE FOUR WATCH ITEMS These are the ways Phase 1 degrades without any individual intake failing. Deep triage quietly reverting to forty-five minutes. The pool being reclaimed. The tracker decaying. Lean being offered too widely because it looks like the win. Review them weekly. All four are recoverable if caught early and very hard to recover if caught at week ten.

## Slide 11
10
The twelve weeks
And the evidence gate at the end of it
The plan
WEEKS 1–2
Prepare
Write the Triage Guide · two calibration sessions · stand up the pool and agree its protection · build the tracker · publish the tier model to partners
>
WEEKS 3–6
Run in parallel
Every new intake gets deep triage and a tier, but is still delivered under the current model. Real data, no delivery risk. Fortnightly calibration.
>
WEEKS 7–10
Operate the tiers
Tier assignments take effect · Lean+ with named guides and two checkpoints · first Lean intakes on the simplest patterns · pattern log begins
>
WEEKS 11–12
Evidence review
Compile the measurements · assess against the approval criteria · present the Phase 2 case built on what actually happened
The parallel run in weeks three to six is deliberate and should not be shortened. It produces distribution and completeness data at zero delivery risk, and it gives the leads four weeks of scoring practice before their assignments start binding real work.
THE EVIDENCE GATE — AGREED IN ADVANCE SO THE WEEK-12 REVIEW IS NOT A NEGOTIATION
Criterion
What good looks like
What it proves
Distribution holds
50%+ of intakes route to Lean or Lean+
The rubric works against live demand, not just a retrospective
Lighter tiers hold
Escalation rate out of Lean and Lean+ below 25%
Tier assignment is accurate enough to rely on
Clarification cycles fall
A measurable reduction against the baseline
The intake intervention works, and is worth automating
Partners accept assigned tiering
Appeal rate below 20%, most unsuccessful
The governance model is viable at scale
The baseline exists
Effort and elapsed time per stage per team
The Phase 2 business case can be quantified
The bottleneck is identified
A quantified statement of where manual effort concentrates
The Phase 2 backlog is evidence-led, not designed
No compliance regression
No increase in findings on completed intakes
The lighter tiers are safe before they are scaled
THE SIXTH CRITERION IS THE ONE THAT SPECIFIES THE BUILD
The first five validate the model. The sixth is what turns the Phase 2 backlog from a design exercise into an evidence-led list — after a quarter of running this by hand, we will know precisely which questions partners stumble on, which rules get applied wrong, which gates get waived and where the hours actually go.
Notes: The plan, and the gate. Weeks one and two: preparation. The guide is the critical path item — one week of two experienced engineers plus a governance analyst. Calibration sessions, pool stood up with its protection agreed, tracker built, tier model published to partners so the rubric is visible before it binds anyone. Weeks three to six: parallel run. This is the part people will want to shorten because it feels like delay. Do not. It produces distribution and completeness data at zero delivery risk, and it gives you four weeks of scoring practice before your assignments start binding real work. You will score differently in week six than in week three, and it is far better that the learning happens here. Weeks seven to ten: the tiers take effect. Lean+ runs properly. The first Lean intakes go to partners who have been through the process before, on the simplest patterns only. Weeks eleven and twelve: evidence review. THE GATE We are stating the criteria now, before we know the answers. That is deliberate — it means the week-twelve review is an assessment against agreed standards rather than a negotiation about whether it went well. Point at the sixth criterion. The first five validate the model. The sixth specifies the build. THE THING TO ASK OF THIS ROOM Over the quarter, keep a running note of where the manual approach hurt. Which question partners consistently stumbled on. Which rule got applied wrong. Which gate got waived and why. Where the hours actually went. That note is the single most valuable artefact Phase 1 produces, and nobody can write it afterwards from memory.