## Slide 1
Partner enablement operating model
Tiered Enablement, in Four Phases
Why one delivery model cannot serve thirty-eight different intakes — and how we fix it without building anything first
PORTFOLIO
38 scenario types · 10 categories
TEAMS
3 squads · 30+ engineers
PHASE 1
One quarter · no build
DECISION
Approve Phase 1
ECM Partner Enablement · Draft for review

## Slide 2
1
Thirty-eight different intakes, one delivery model
Every intake receives a dedicated pod from inception to release, regardless of what it actually requires
The problem
THE INTAKE PORTFOLIO — TEN CATEGORIES, THIRTY-EIGHT DISTINCT SCENARIO TYPES
Intake category
Types
Effort
ECM days
New partner onboarding (greenfield)
4
High
35–60
New document types / content extension
7
Medium
8–20
Channel & integration additions
5
High
20–40
Volume & performance uplift
3
Medium
10–18
Metadata & data model changes
4
Medium
8–16
Intake category
Types
Effort
ECM days
Retention & records changes
3
High
15–30
Security & access changes
3
Low
4–8
Environment & cutover requests
3
Low
3–6
Migration & remediation campaigns
2
High
40–90
Support & ownership changes
4
Low
2–5
WHERE AN ENABLER SQUAD MEMBER'S TIME ACTUALLY GOES ON A TYPICAL INTAKE
18%
Design judgement
24%
ECM build & config
31%
Chasing partner-owned inputs
15%
Chasing external teams
12%
Tracking & admin
A DEDICATED RESOURCE IS A SUBSIDY FOR INCOMPLETE INTAKE
Forty-six per cent of an enabler squad member's time is chasing rather than engineering — and two thirds of that is for inputs the partner owns: document inventory and samples · volume and peak projections · retention requirements and their regulatory basis · the business meaning of metadata · the entitlement model · test data · UAT participants · the support and on-call owner. Because someone is always assigned to chase, the cost of supplying none of it up front falls on us instead of on the partner.
THE REAL GAPS IN AN ALWAYS-DEDICATED MODEL
Depth is uniform, need is not
10 of the 38 types need under ten ECM days. Every one is given a full pod anyway.
The hard intakes are starved
The 14 genuinely complex types compete for the same attention as 24 that are not.
Responsibility transfers quietly
With someone always assigned to chase, the partner never feels the cost of an incomplete intake.
Growth has only one answer
Capacity = demand × fixed depth. Every uplift in partner demand becomes a headcount request.
The effort split is the squads' own estimate, not a measurement — we do not currently instrument it, and producing that measurement is an explicit Phase 1 deliverable. The direction is not in doubt; the magnitude is what the quarter is for.
Notes: PURPOSE OF THIS SLIDE Establish that the problem is structural, that it is ours rather than the partners', and that it is visible in the portfolio itself. Do not move on until the room accepts the diagnosis — nothing on the following six slides lands without it. THE PORTFOLIO — START HERE We support thirty-eight distinct onboarding scenario types, which group into ten categories. Walk a few rows rather than all ten. The spread is the point: a support ownership change takes two to five ECM days; a greenfield partner onboarding takes thirty-five to sixty; a migration campaign takes forty to ninety. That is a twenty-fold range, and every single one of them is handled with the same dedicated pod from inception to release. Ten of the thirty-eight types need under ten ECM days. Fourteen are genuinely high-effort. Fourteen sit in the middle. One delivery model is being asked to serve all three groups. THE EFFORT SPLIT — THE HEART OF THIS SLIDE Of an enabler squad member's time on a typical intake: eighteen per cent is design judgement, twenty-four per cent is ECM build and configuration, thirty-one per cent is chasing inputs the partner owns, fifteen per cent is chasing external teams, and twelve per cent is tracking and admin. Say the headline plainly: forty-six per cent is chasing, not engineering. And the largest single block — thirty-one per cent — is spent chasing things that are the partner's own responsibility to supply. Be scrupulous here, because someone will push: this is the squads' own estimate. We do not instrument it today. Producing the measurement is a named Phase 1 deliverable. Concede the precision immediately and hold the direction. WHAT WE ARE ACTUALLY CHASING FOR — READ THE LIST OUT Document inventory and sample files. Volume and peak projections. Retention requirements and the regulatory basis for them. The business meaning of metadata attributes. The entitlement model for their own users. Test data. UAT participants. The support and on-call owner after go-live. Every item on that list is the partner's to provide. None of it requires ECM engineering knowledge to answer. We are paying engineers to extract information that the requesting party already holds. THE SUBSIDY ARGUMENT — THIS IS THE KEY INSIGHT This is the line to land: a dedicated resource is a subsidy for incomplete intake. Because we always assign someone, and that someone always chases, the partner never experiences any consequence from supplying nothing up front. We have, without ever deciding to, taken on their requirements-gathering as our own work. The model does not merely waste our capacity — it actively removes the incentive for the partner to arrive prepared. If someone suggests we simply ask partners to do better: we have, repeatedly. Exhortation does not change a system where the cost of non-compliance falls on someone else. The tiered model changes it by making the obligation explicit and attaching it to what the partner receives. THE FOUR GAPS Depth is uniform, need is not — ten types need under ten days and all of them get a pod. The hard intakes are starved — the fourteen genuinely complex types are competing for attention with twenty-four that are not. This is the one engineers in the room feel most sharply, and it is worth pausing on: the model over-serves the simple and under-serves the difficult simultaneously. Responsibility transfers quietly — the subsidy argument above. Growth has only one answer — capacity equals demand multiplied by a fixed depth, so every increase in partner demand arrives as a headcount request. That is why this conversation has happened before and ended the same way. A FIFTH GAP, IF IT COMES UP Without a published rule, depth gets allocated by influence: the partner who escalates hardest gets the pod. Nobody designed that, but it is what happens when there is no objective basis for saying no. LIKELY QUESTIONS "Are the squads just slow?" No. They are applying maximum depth uniformly and spending half their time chasing. This is an allocation problem, not a throughput problem. "Could we hire our way out?" Only temporarily. Linear scaling means every demand increase needs a proportional headcount increase, and the chasing fraction does not improve with scale. "Why thirty-eight?" That is the catalogue of distinct scenario types, not live intakes. Each type recurs. "Where do the day ranges come from?" Squad estimates against recent deliveries of each type. Illustrative, and Phase 1 replaces them with measurement.

## Slide 3
2
The solution: make engineering depth a variable
Four enablement tiers assigned by ECM against a published rubric — each with its own checkpoints, guardrails and partner obligations
The model
WHAT THE TIERED MODEL CHANGES
Depth matches assessed need
Engineering depth becomes a variable set by a published rubric, instead of a constant applied to everything.
Capacity stops scaling linearly
Lean costs almost nothing per intake and one shared pool serves every Lean+ intake, so demand growth stops meaning headcount growth.
Partner obligations become explicit
Each tier states what the partner must do to receive it. Responsibility stops transferring silently to whoever was assigned.
Allocation stops being political
A published rubric with hard overrides replaces escalation. An appeal argues a determinant, never importance or urgency.
THE FOUR TIERS — WHAT ECM ALLOCATES, THE CHECKPOINTS THAT APPLY, AND THE GUARDRAILS THAT BIND THEM
Tier
ECM allocates
Checkpoints
Guardrails specific to the tier
Steady
Lean
No dedicated capacity
Entry check at triage — pattern confirmed and completeness band met. Exit check before go-live. No scheduled design review.
All eight invariants, evidenced by checklist · any deviation from the pattern forces escalation to Lean+ · partner must already have completed one prior intake.
16
Lean+
A shared pool, part-time
Two mandatory design checkpoints — solution shape after triage, build readiness before configuration — plus a pre-go-live gate walk.
All eight invariants · the named guide signs the design record · no artefact means no review, rebook · scope beyond the pattern forces a re-tier.
13
Dedicated
A full pod, inception to release
Continuous: architecture review · design authority sign-off · integration readiness · pre-UAT · pre-go-live · post-go-live review.
All eight invariants plus full design authority review · a joint delivery plan with the partner · formal change control on any scope movement.
7
Factory
A campaign team, time-boxed
Campaign entry certification · mid-campaign sampling audit · campaign exit certification.
All eight invariants applied to a batch remediation standard signed off once per campaign · sampling assurance to a defined confidence level.
2
A LIGHTER TIER IS A LIGHTER ALLOCATION OF JUDGEMENT — NEVER A LIGHTER STANDARD
All four tiers meet the same eight compliance invariants: classification determination · retention approval · security and access review · volume certification · promotion ladder · support acceptance · audit trail · new document type re-review. What changes between tiers is how much design judgement ECM allocates to reaching them, and how that judgement is scheduled. Tier is assigned by ECM against a seven-determinant rubric with hard overrides — never chosen by the partner, and appealable on a determinant but not on preference.
Notes: PURPOSE OF THIS SLIDE Define the model precisely enough that the room could apply it, and make the compliance position unambiguous. This is the slide people will come back to. THE FOUR ADVANTAGES — LEAD WITH THESE Depth matches assessed need. The second term of the capacity equation stops being a constant. That is the structural change; everything else follows from it. Capacity stops scaling linearly. A Lean intake costs us almost nothing, and one shared pool of four to six people serves every Lean+ intake concurrently. So partner demand can grow without a proportional headcount request — which is the thing this room has been unable to say yes to before. Partner obligations become explicit. This is the direct answer to the subsidy problem on the previous slide. Each tier states what the partner must do in order to receive it: follow the published pattern, attend both checkpoints with artefacts prepared, commit to a joint delivery plan. The obligation is attached to what they get, so it is not an exhortation. Allocation stops being political. A published rubric with hard overrides replaces escalation. An appeal has to name a determinant it believes was scored wrongly — it cannot argue that the intake is important, because every partner believes that. THE TIER TABLE — WALK IT BY COLUMN Read down the columns, not across the rows. The columns are the dimensions along which the tiers actually differ. What ECM allocates: nothing, a part-time shared pool, a full pod, a time-boxed campaign team. That is the capacity decision and it is the whole point of the model. Checkpoints: this is the column people most want to understand. Lean has two binary checks and no scheduled design review at all — an entry check confirming the pattern and completeness band, and an exit check before go-live. Lean+ has two mandatory design checkpoints at defined moments, solution shape after triage and build readiness before configuration starts, plus the gate walk. Dedicated has continuous involvement with six named review points. Factory is certified at campaign boundaries with a sampling audit in the middle, because per-item review would defeat the purpose of batching. Guardrails: note that every row begins with "all eight invariants". What differs is the tier-specific binding. Lean's is the escalation trigger — any deviation from the pattern forces a move to Lean+, which is what makes a no-review tier safe. Lean+'s is that the named guide signs the design record and no artefact means no review. Dedicated adds full design authority and formal change control. Factory binds a remediation standard once per campaign rather than per item. THE TWO RULES THAT MAKE IT WORK First: the Lean escalation trigger. A tier with no scheduled design review is only defensible because deviation from the pattern is itself a trigger. Make this explicit if anyone is nervous about Lean. Second: the prior-intake condition. A partner that has not been through one onboarding with us cannot be Lean, whatever the scenario looks like on paper. That is about partner maturity, not intake complexity. THE INVARIANTS — DO NOT SKIP The band at the foot is the most important sentence here for anyone with a compliance interest. A lighter tier is a lighter allocation of design judgement to reach the same standard, not a lighter standard. Say it in those words. The first instinct of a partner told they are "Lean" is to hear deprioritisation, and the first instinct of a records or security stakeholder is to hear corner-cutting. Both are wrong and both will happen unless pre-empted. ASSIGNMENT IS NOT NEGOTIABLE Assigned by ECM, against a published rubric, with hard overrides. A model where partners self-select collapses within two months. Publishing the rubric is what makes assignment defensible rather than arbitrary. LIKELY QUESTIONS "What if a Lean intake turns out to be complex?" It escalates, and we track the rate. Above twenty-five per cent the rubric is wrong and we recalibrate. "Who can override a tier?" Nobody on request. Five hard conditions force Dedicated regardless of score — no pattern precedent at all, content or metadata to be remediated, new regulated retention or WORM, multiple LOBs or partners in one intake. And no first-time partner can be Lean. "Does Factory really belong here?" It is campaign-shaped rather than intake-shaped, so it behaves differently — but it is listed because those two scenario types otherwise distort every figure. "Is this just triage with new labels?" No. Triage today classifies and routes. Here it determines how much engineering depth an intake receives, which is a resourcing decision with a published basis and an appeal route.

## Slide 4
3
Phase 1 — run the tiered model entirely by hand
One quarter of operating discipline using the people and the knowledge we already have. Nothing is built
Phase 1
PHASE 1
Evaluate
DEPENDENCY
ECM leadership only
BUILDS
Nothing at all
DURATION
One quarter
THE PARTNER'S JOURNEY THROUGH AN INTAKE IN THIS PHASE
ECM drives
Shared
Partner drives
Raise the intake
Partner raises it; ECM triage classifies and routes.
ECM DRIVES
>
Establish requirements
90-minute Discovery Triage from a written guide; every gap dated and owned.
SHARED
>
Build & configure
Pod, shared pool or published pattern, by assigned tier.
ECM DRIVES
>
Clear the gates
Checklist walked by lead and pool; every waiver recorded.
ECM DRIVES
>
Go live & support
ECM-led cutover, handover and support acceptance.
ECM DRIVES
WHAT CHANGES IN THIS PHASE
AUTOMATION, AI AND AGENTIC CAPABILITY
Six workstreams of operating discipline, one of design
Tier model published and socialised to the three squads and the partner community.
Triage template rebuilt around the 54-point question set, every item carrying its reason.
Triage leads assign the tier and select the guardrails, with the basis recorded.
Partner tier charter issued with every assignment — what you receive, what you owe, why this tier.
A shared pool of four to six stood up from the three existing squads.
Governance, approvals and a waiver log reviewed fortnightly.
None — and deliberately so
Nothing is built, nothing is procured, no agent is deployed. Every mechanism the model needs has a human equivalent we already have the knowledge to run.
The only forward-looking work is design, not construction: an architecture evaluation that specifies and costs Phase 2 — target architecture, the agentic authority model, the integration inventory and a build estimate.
That is roughly two weeks of architect time spread across the quarter, and it is why Phase 1 ends with a costed proposal rather than a request for more time.
P1 VALUE ADD
Depth stops being uniform
17 scenarios move from a continuous pod to scheduled design assurance; Dedicated falls from 38 to 14.
Clarification cycles fall on the deeper triage alone, and long-lead items are raised at triage rather than mid-build.
The first measured effort and elapsed-time baseline we have ever had.
Better than today: the 14 genuinely complex intakes stop competing with 24 that are not — at a cost of about two weeks of writing.
What Phase 1 cannot fix
The clerical load is untouched — artefacts, routing and tracking all stay manual.
Per-intake effort stays roughly constant, so the model still does not scale with demand.
The partner still cannot act unaided, and external queue time is unchanged.
Guardrails are enforced by people under schedule pressure, so they can still be waived.
Notes: PURPOSE OF THIS SLIDE Show that the model can be run for a quarter at close to zero cost, and be scrupulously honest about its ceiling. Phase 1 is the only thing being approved today. THE JOURNEY STRIP — ESTABLISH THE BASELINE Four of the five stages are ECM-driven and the fifth is shared. That is the starting state, and it is the picture that will visibly change across the next three slides. Point at it and say: this is what "we are in the middle of everything" looks like. The one stage that does change in Phase 1 is establishing requirements, and it changes by becoming a real conversation rather than a form. A pre-read, a ninety-minute Discovery Triage worked from a written guide with the reason explained at the point of asking, a thirty-minute internal tiering review, and a one-page Outcome Record. Roughly three hours of structured effort per intake, against weeks of serial clarification today. THE SIX-PLUS-ONE WORKSTREAMS Six are operating discipline: socialising the model; rebuilding the triage template; leads assigning tier and guardrails; the partner tier charter; the shared pool; and the governance wrapper. The partner tier charter is the one that addresses the subsidy problem directly. It states per tier what the partner receives, what is expected of them in return, and the basis on which the tier was assigned. A partner who understands why they are in Lean+ will accept it; one who is merely informed will escalate, and will be right to. The seventh is the architecture evaluation — design only. If someone asks what architects do during a no-build quarter, this is the answer. ON "NOTHING IS BUILT" Be unambiguous. No platform, no workflow engine, no AI, no agents, no partner portal, no integration work, no new headcount. The artefacts produced are written guidance, a scoring sheet, a tracker and a design document. The reason this is credible: six of the seven workstreams are people writing down what they already know and then applying it consistently. That is days of work, not months, which is why Phase 1 can start on approval rather than on a funding cycle. THE TWELVE WEEKS Weeks 1–2 prepare. Weeks 3–6 run in parallel — every intake gets deep triage and a tier assignment but is still delivered the current way, so we get real data at zero delivery risk and the leads get four weeks of scoring practice. Weeks 7–10 the assignments take effect. Weeks 11–12 evidence review. Defend the parallel run if anyone proposes shortening it; it is the most tempting and most damaging cut available. THE CEILING — GIVE THIS EQUAL WEIGHT Present the right-hand card with the same energy as the left. The clerical load is untouched. Per-intake effort stays roughly constant, so the model does not scale. The partner still cannot act unaided. External queue time is unchanged. And guardrails applied by a person under schedule pressure are weaker than gates that block — they will be waived, and the defence is that every waiver is recorded and reviewed, not that none will happen. Why this honesty matters: a phase that oversells itself cannot be trusted at the week-twelve review, and the ceiling is precisely what motivates Phases 2 to 4. LIKELY QUESTIONS "Why do you need the pool if nothing is being built?" Because Lean+ carries most of the Phase 1 gain — seventeen scenarios — and Lean+ is defined by scheduled design assurance from someone who is not the delivery team. No pool, no Lean+, and Phase 1 becomes a renaming exercise. "What if it does not work?" We will have a measured baseline, a calibrated rubric and a clear statement of why, for about two weeks of writing. That is a far cheaper way to find out than four sprints into a build. "Why only five Lean?" Lean+ is a human process by design and works well by hand. Lean assumes the partner can proceed unaided, which without tooling they cannot — so only the five simplest, most repeated patterns qualify.

## Slide 5
4
Phase 2 — automate and AI-enable everything inside ECM
Scoped by what we own outright, so no external team's roadmap can delay it — and the partner begins to self-serve
Phase 2
PHASE 2
Automate inside ECM
DEPENDENCY
ECM engineering only
BUILDS
What ECM owns outright
AI
Agentic, inside the perimeter
THE PARTNER'S JOURNEY THROUGH AN INTAKE IN THIS PHASE
ECM drives
Shared
Partner drives
Raise the intake
Partner raises it unaided through a guided intake.
PARTNER DRIVES
>
Establish requirements
AI copilot asks the catalogue questions and explains why each is needed.
SHARED
>
Build & configure
ECM artefacts generated from the matched pattern.
ECM DRIVES
>
Clear the gates
ECM gates enforced by the gate engine; external gates still manual.
ECM DRIVES
>
Go live & support
ECM-led, but with live state visible to the partner.
ECM DRIVES
WHAT CHANGES IN THIS PHASE
AUTOMATION, AI AND AGENTIC CAPABILITY
Everything inside the ECM perimeter
Guided intake with the why-register — completeness enforced at source rather than discovered in week six.
Gap register that ages open items, chases owners and escalates on the due date.
Tiering assistant scores the determinants and proposes a tier; the lead still decides.
Pattern matcher and automatic scope derivation from the catalogue seeded in Phase 1.
ECM artefacts generated: repository definitions, metadata mappings, retention bindings, configuration.
Partner cockpit — read-only state, open gaps, next action and due dates.
Agentic, with authority that stops at the perimeter
An Onboard360AI orchestrator with sub-agents bounded strictly by the ECM perimeter: intake copilot, completeness agent, tiering assistant, pattern matcher, scope composer, artefact generator, gate checker.
The authority boundary is architectural, not a setting: agents propose and prepare, a named person decides, and anything irreversible or compliance-bearing takes a second explicit authorisation.
No agent holds a credential that can promote, approve or clear. If one is wrong, the blast radius is a bad proposal that a person rejects.
P2 VALUE ADD
The data deficit attacked at source
Completeness enforced at intake — this is the intervention aimed squarely at the 31% spent chasing partner-owned inputs.
ECM artefacts generated rather than assembled, which removes the clerical load Phase 1 could not touch.
Three scenarios move Lean+ to Lean as self-service becomes possible on proven patterns.
Better than Phase 1: effort per intake finally falls, instead of only being better aimed at the right intakes.
What Phase 2 still leaves
Every external hand-off is still a manual submission into another team's queue.
Those queues become the dominant share of elapsed time once our own effort has fallen.
Dedicated does not move at all — automating our work does not make a complex intake less complex.
Phase 2 makes ECM efficient. It does not yet make onboarding fast.
Notes: PURPOSE OF THIS SLIDE Show the first real build, explain why its scope is drawn where it is, and set the compliance position on AI before anyone has to ask. THE JOURNEY STRIP — THE FIRST GREEN Compare it with the previous slide. "Raise the intake" has moved to partner-driven: they initiate unaided through a guided intake instead of raising a ticket and waiting for triage. "Establish requirements" is now genuinely shared, with an AI copilot asking the catalogue questions and explaining why each one matters, while ECM assures the result. The last three stages are still ours. That is the honest picture of Phase 2: the front of the journey opens up, the back does not. WHY THE SCOPE IS DRAWN HERE Everything in this phase is owned, specified and operated by ECM. Nothing requires another team to change an interface, commit roadmap capacity or agree a contract. That was a deliberate design constraint, not an accident. The reason is delivery risk: a phase needing seven external teams to commit capacity has seven ways to stall. Confining Phase 2 to the perimeter guarantees we can deliver on our own schedule, and means we arrive at Phase 3 with a working system to integrate rather than a design to discuss. It costs us something real — external queue time is untouched until Phase 3 — and that trade is worth stating openly. THE CAPABILITIES — MAP THEM TO PHASE 1 Each one mechanises something the room will have spent a quarter doing by hand. The written guide becomes a guided intake. A lead's judgement on completeness becomes a gate that blocks. A spreadsheet column becomes a gap register that ages and chases. A scoring sheet becomes a tiering assistant. A lead's recall becomes a pattern matcher. Templates filled in by hand become generated artefacts. That mapping is deliberate: Phase 2 is not a new idea, it is the mechanisation of a process we will already have ten weeks of evidence about. Two deserve emphasis. Completeness validation becomes a block rather than advice — a person under pressure lets things through and a gate does not. And artefact generation is where the clerical load finally goes. THE AI AUTHORITY MODEL — DO NOT RUSH THIS Four layers: propose, decide, act, authorise. An agent may do a great deal in propose and act, but the transition always passes through a named human, and anything irreversible requires a second authorisation. The point that converts sceptics: this is architectural, not a policy an operator can relax under delivery pressure. No agent holds a credential capable of promoting, approving or clearing anything. The capability is simply absent. Worth saying directly to compliance stakeholders: every determination stays with its existing owner. Imaging Governance still determines trust posture and allocates classification; Records Management still approves retention. The tiering assistant can score all seven determinants and show its reasoning, but it cannot assign — the lead assigns, every time. Expect a question about hallucination in the intake copilot. Its drafts are proposals the partner must confirm, each attributed to the prior intake it was derived from, and nothing enters the record unconfirmed. THE BOUND — SAY THE LINE VERBATIM "Phase 2 is the phase that makes ECM efficient. It is not the phase that makes partner onboarding fast." Saying that at the Phase 2 approval protects us from being judged at the end of Phase 2 against a Phase 4 expectation. Be concrete: a partner who previously waited six weeks, four on us and two on Imaging Governance, now waits perhaps three — of which two are still Imaging Governance. Real improvement, but not the improvement they were promised. WHY DEDICATED DOES NOT MOVE It looks like an error on the next slide's chart, so explain it here. The determinants that drive a Dedicated assignment are mostly external in origin — new regulated retention, DKE changes, uncertified volume envelopes. Automating our own work makes those intakes cheaper to run without making them less complex.

## Slide 6
5
Phase 3 — orchestrate across the boundary
Contract-first integration with the in-house teams every onboarding depends on, so queue time stops dominating the timeline
Phase 3
PHASE 3
Orchestrate outward
DEPENDENCY
In-house partner teams
BUILDS
Across the boundary
AI
Agents assemble, validate, chase
THE PARTNER'S JOURNEY THROUGH AN INTAKE IN THIS PHASE
ECM drives
Shared
Partner drives
Raise the intake
Partner raises it unaided through a guided intake.
PARTNER DRIVES
>
Establish requirements
Copilot-guided, with long-lead items identified and raised on day one.
PARTNER DRIVES
>
Build & configure
ECM artefacts generated; external provisioning requested in parallel.
ECM DRIVES
>
Clear the gates
External requests assembled, validated and tracked end to end.
SHARED
>
Go live & support
ECM-led, with every dependency visible and chased.
ECM DRIVES
WHAT CHANGES IN THIS PHASE
AUTOMATION, AI AND AGENTIC CAPABILITY
Every hand-off outside the ECM perimeter
Contract-first integration with Imaging Governance, Records Management, Security, Apigee, KEES, DCT and SPLI.
Requests assembled from the intake record and validated against each team's acceptance criteria before submission.
Long-lead items — DKE changes, new retention bindings, SPLI certification — raised at triage rather than at the point of need.
Status tracked, SLAs measured, escalation automatic on breach.
What we ask of those teams is modest: written acceptance criteria, a structured channel, a readable status signal.
Agents that assemble and chase, but never decide
Agents build each external request from the intake record, check it against the receiving team's published acceptance criteria, submit it, track status and chase on SLA breach.
They influence no determination whatsoever. Imaging Governance still determines trust posture and allocates category, type and subtype; Records Management still approves retention and certifies WORM.
What changes is that requests arrive complete, well-formed and explained — which converts a three-cycle hand-off into a one-cycle hand-off.
P3 VALUE ADD
Queue time stops dominating
Rework cycles with external teams removed — the single largest source of avoidable elapsed time once our own effort has fallen.
The 15% of squad time spent chasing external teams largely disappears.
Dedicated finally moves, 14 to 11, as external complexity becomes routine rather than bespoke.
Better than Phase 2: cuts waiting, which is a different quantity from effort and which no ECM automation can reach.
What Phase 3 still leaves
The partner still depends on us to initiate every build step; the cockpit remains read-only.
Eleven scenarios stay Dedicated because they involve genuine novelty, and orchestration cannot make a novel problem routine.
The accumulated backlog still competes with new demand for the same capacity.
Our dependency on external SLAs is now measured rather than hidden — an improvement, but not control.
Notes: PURPOSE OF THIS SLIDE Show the phase where elapsed time genuinely falls, and be clear that the mechanism is simpler than it looks: send complete, well-formed requests the first time. EFFORT VERSUS WAITING — THE CONCEPTUAL KEY Open with this. A perfectly efficient ECM team still waits three weeks for a classification determination. That wait is invisible to every internal efficiency metric and completely visible to the partner. Phases 1 and 2 reduce effort; this phase reduces waiting, and they are different quantities. THE MECHANISM — WALK ONE HAND-OFF END TO END Use Imaging Governance, since it is the most consequential and most familiar. Today we submit a document inventory, and Imaging Governance comes back asking about sample traits or proposed subtypes — that round trip costs a full queue cycle, and it can happen twice. Under Phase 3 the request arrives with the inventory, the sampled traits, a proposed category, type and subtype allocation and the trust rationale, already checked against whether every type exists in the taxonomy and whether a DKE change is implied. We are not speeding up the receiving team at all. We are removing the rework loop that currently multiplies the effective queue time. WHAT WE ASK OF THE EXTERNAL TEAMS — USE THIS WHEN SOCIALISING Three things: their acceptance criteria written down, a structured intake channel, and a status signal we can read. We are not asking them to change process, adopt our tooling or commit engineering capacity. That modest ask is precisely why this phase is realistic to sequence third rather than first — and it is in their interest too, since they stop receiving half-formed requests. Plan the conversation during Phase 2, not at the start of Phase 3. This is the dependency most likely to bite, and the mitigation is descoping per team rather than delaying the whole phase. THE AGENTIC ROLE — BE PRECISE Agents assemble, validate, submit, track and chase. They influence no determination. Say that plainly to Imaging Governance and Records Management early, because the instinct on hearing "AI" and "classification" in the same sentence is that we are proposing to automate their judgement. We are not. Their authority is untouched. WHY DEDICATED MOVES HERE AND NOT IN PHASE 2 The three scenarios that reclassify were Dedicated because of external complexity — new subtypes needing DKE assessment, a new retention binding, an uncertified volume envelope — not because the ECM work was hard. Once those hand-offs are routine, well-formed and predictable, the intake is not complex any more. THE PARTNER-FACING POINT This is the first phase a partner would actually notice. Phases 1 and 2 improve how we work; this one shows up in the only measure a partner experiences, which is how long it takes from raising an intake to being live. If the programme is going to be judged on partner-facing results, this is the phase that earns that judgement, and it is worth saying so when asking for it. THE HONEST BOUND Eleven scenarios stay Dedicated and will stay Dedicated through Phase 4, because they involve genuine novelty. That is the irreducible floor. We should stop implying it can be engineered away.

## Slide 7
6
Phase 4 — partner self-service, and tiers used as designed
Take ECM out of the middle for everything that does not need us there, and drain the accumulated backlog through it
Phase 4
PHASE 4
Partner self-service
DEPENDENCY
The partners themselves
BUILDS
Partner-facing
AI
Guided; judgement gates retained
THE PARTNER'S JOURNEY THROUGH AN INTAKE IN THIS PHASE
ECM drives
Shared
Partner drives
Raise the intake
Partner initiates against a proven pattern, no conversation needed.
PARTNER DRIVES
>
Establish requirements
Self-served with guidance; the pattern carries most of the answers.
PARTNER DRIVES
>
Build & configure
Partner provisions within pre-approved policy bounds.
PARTNER DRIVES
>
Clear the gates
Partner clears deterministic gates; judgement gates stay with ECM.
SHARED
>
Go live & support
Partner-led, with ECM on escalation only.
PARTNER DRIVES
WHAT CHANGES IN THIS PHASE
AUTOMATION, AI AND AGENTIC CAPABILITY
Self-service, plus the discipline to use the tiers properly
Partners instantiate a proven pattern and initiate without a conversation.
Provisioning within pre-approved policy bounds; anything outside them still comes to us.
Self-serve clearance of gates with deterministic criteria — every judgement gate and all eight invariants stay with ECM.
Guided remediation from published diagnostics before escalating.
Dedicated pods reserved for the seven scenarios that genuinely need them; the shared pool sized on measured load.
The accumulated backlog drained through self-service rather than competing for pod capacity.
Guided self-service, with judgement never handed over
Partner-facing guidance: pattern recommendation, requirement explanation, diagnostics for common failures, and next-action prompts.
The precondition that makes this responsible rather than reckless: self-service only sits on gates that are deterministic, automated and trustworthy — which is exactly what Phases 2 and 3 produce.
Judgement gates are never handed over, and pattern deviation always forces a conversation with ECM rather than a warning the partner can dismiss.
P4 VALUE ADD
Partners stop waiting on us
Lean becomes genuinely self-service at 16 scenarios; Dedicated settles at 7, reserved for real novelty.
The backlog drains through a separate route instead of competing with new demand for the same pods.
Released capacity absorbs demand growth — this is a growth argument, not a headcount-reduction one.
Better than Phase 3: turnaround improves for the partner, not only cost for us.
What remains, permanently
Seven scenarios need a dedicated pod and always will — genuine novelty cannot be patterned.
Tier utilisation discipline is an organisational commitment, not a build, and is the easiest part to let slip.
Self-service widens the blast radius of a bad pattern, so pattern curation becomes a standing ECM responsibility.
Notes: PURPOSE OF THIS SLIDE Close the arc: the partner journey is now almost entirely partner-driven, and ECM has moved from doing the work to assuring it. Give equal time to the second half of this phase, which is organisational rather than technical and is the part most likely to be neglected. THE JOURNEY STRIP — THE PAYOFF Compare all four phase slides side by side if you can. Phase 1: four of five stages ECM-driven. Phase 4: four of five partner-driven, with gates shared. That progression is the programme in one picture, and it is worth pausing on. Note what stays shared: clearing the gates. That is deliberate and permanent. Deterministic gates can be cleared by the partner; judgement gates cannot, and never will be. WHAT ECM RETAINS — WALK THIS COLUMN, NOT THE OTHER It is what reassures the room. Pattern curation stays with us. The policy bounds stay with us. Every judgement-bearing gate stays with us. All eight invariants stay with us. Only own-state visibility is pure handover — and that is also the thing partners would value most today. THE SECOND HALF — TIER UTILISATION DISCIPLINE This is an organisational commitment, not a build, which is exactly why it gets neglected once the tooling is delivered. Dedicated pods reserved for seven scenarios. The shared pool sized on measured checkpoint load rather than estimate. The backlog drained through self-service instead of competing with new demand for the same pods. None of that requires technology. It requires holding the line, and the line will be tested. THE PRECONDITION — THE GOVERNANCE ANSWER Self-service is only responsible on top of gates that are deterministic, automated and trustworthy. Producing those is precisely what Phases 2 and 3 do. This is the strongest single justification for the phase ordering, and it is worth repeating here even though it was made earlier: handing partners self-service before the gates were reliable would transfer risk to the party least equipped to carry it. A NEW RISK THIS PHASE INTRODUCES Self-service widens the blast radius of a bad pattern. When one partner follows a flawed pattern with a pod alongside them, someone notices. When forty partners self-serve on it, nobody does until something breaks. Pattern curation therefore becomes a standing ECM responsibility with its own review cadence — it is not a one-off Phase 4 deliverable. ON CAPACITY — BE CONSISTENT Released capacity absorbs demand growth. Say it that way every time. Framing it as headcount reduction will make the squads resist every phase of this programme, including the one we are asking approval for today. LIKELY QUESTIONS "What stops a partner self-serving something complex?" The rubric runs at intake. Anything scoring above the Lean threshold, or hitting a hard override, never reaches self-service in the first place. "What if the backlog does not drain?" Measure it separately from new-intake turnaround. The two have different dynamics and averaging them hides both. "Do we still need the shared pool?" Yes — thirteen Lean+ scenarios at steady state. What changes is that we can finally size it on measured checkpoint load instead of estimating.

## Slide 8
7
The compounding view, and what we are asking for today
Four phases, four kinds of waste removed, four standalone gains — and an approval limited to the first of them
The ask
TIER DISTRIBUTION ACROSS THE FOUR PHASES
Today
38
After Phase 1
5
17
14
After Phase 2
8
14
14
After Phase 3
12
13
11
After Phase 4
16
13
7
Lean
Lean+
Dedicated
Factory
ILLUSTRATIVE SHAPE — PARTNER TURNAROUND, TODAY = 100
Today
100
Phase 1
82
Phase 2
64
Phase 3
46
Phase 4
32
A shape, not a forecast — Phase 1 produces the first measured baseline and these are then replaced.
WHAT PHASE 1 COSTS — THE ONLY PHASE BEING APPROVED TODAY
~2 wks
of preparation
Two engineers and a governance analyst, writing guidance they already hold.
0
new headcount
The shared pool is seconded from the three squads we already have.
0
lines of code
Nothing is built. The Phase 2 architecture is designed and costed only.
1 qtr
to a decision
Twelve weeks, then approve or decline Phase 2 against the evidence.
WHAT WE ARE ASKING THIS ROOM TO APPROVE
1 Run Phase 1 for one quarter — the operating discipline, not a build.
2 Protect the shared pool from reclaim by the squads, with a named escalation route agreed before we start.
3 Agree the evidence criteria now, and take the Phase 2 decision against them at week twelve.
What would justify Phase 2
Distribution holds — half or more route to Lean or Lean+ · lighter tiers hold, escalation under 25% · clarification cycles measurably down · partners accept assigned tiering · the effort baseline exists · the bottleneck is quantified · no compliance regression.
Notes: PURPOSE OF THIS SLIDE Bring the four phases together, then narrow the ask to one quarter. The room should leave clear that they are approving a quarter of practice, not a programme. THE DISTRIBUTION CHART Five states, thirty-eight scenarios in each. Dedicated falls thirty-eight, fourteen, fourteen, eleven, seven. The first drop — thirty-eight to fourteen — costs no engineering at all, and that is the single most striking number in the deck. Point out the flat step at Phase 2 before anyone asks. It looks like an error and is not: automating our own work makes dedicated intakes cheaper to run without making them less complex, because the determinants driving a Dedicated assignment are mostly external in origin. Complexity falls at Phase 3, when those hand-offs become routine. THE TURNAROUND INDEX A shape, not a forecast. It derives from the squads' own estimates and we have no measured baseline — which is precisely why Phase 1 exists. If challenged, do not defend the numbers; agree they are estimates and point out that producing defensible figures is a Phase 1 deliverable. Defending illustrative numbers as if they were measured is the fastest way to lose this room. THE FOUR WASTES, IN ONE SENTENCE EACH Phase 1 removes misallocation. Phase 2 removes our own effort. Phase 3 removes waiting. Phase 4 removes mediation. No phase substitutes for another, which is why none of them can simply be skipped to reach the end state faster. THE THREE ASKS — SAY THEM AS THREE One: run Phase 1 for a quarter. Two: protect the shared pool. Three: agree the evidence criteria now. The second is the one most likely to be waved through and most likely to kill this. The pool is four to six people seconded from three squads already under delivery pressure. The first time a squad lead reclaims their person for a sprint commitment and it is allowed, the pool becomes notional and Lean+ silently reverts to unsupported self-service. We are asking for an explicit commitment with a named escalation route agreed before we start — not goodwill. The third protects everyone. Agreeing criteria in advance makes the week-twelve review an assessment rather than an argument, and means a genuine negative result is as useful as a positive one. WHAT WE ARE NOT ASKING FOR No build funding. No headcount. No commitment to Phases 2 to 4. Those are sized by the architecture evaluation inside Phase 1 and come back to this room as a separate, costed proposal. Saying this explicitly makes the ask much easier to approve. IF THE EVIDENCE IS MIXED AT WEEK TWELVE We bring the measurements and recommend either a narrower Phase 2 scope or a second quarter of Phase 1 with named corrections. A mixed result is a steer, not a stop. ON CAPACITY AND HEADCOUNT Released capacity absorbs demand growth. Never frame any phase as headcount reduction — the squads will resist all four phases if they hear it that way, and the honest argument is the growth one anyway: this is how we serve more partner demand with the team we have. CLOSING LINE Each phase stands on its own, each is approved on the evidence the previous one produced, and no phase asks for agreement from a circle wider than the one it has already earned. If the room takes away one sentence, that is the one.