## Slide 1
ECM PARTNER ENABLEMENT · DESIGN WALKTHROUGH
Game Plan, Architecture and Operating Model
For architects and enabling squad leads — the full design behind the tiered model,
the platform capability, the guardrails and the four-sprint plan
ENABLEMENT MODELS
Lean · Lean+ · Dedicated · Factory
INTAKE DATA POINTS
54 across 10 categories
SCENARIOS TIERED
38, with determinants
BUILD HORIZON
4 sprints · 5–6 people

## Slide 2
1
The problem, in one slide
Two independent causes. Different fixes, different timescales.
Context
Capacity required = concurrent intakes × a fixed engineering depth applied to every intake
CAUSE 1 · IMMEDIATE FIX
The data deficit
Requirement for a data point is discovered incrementally, after intake has landed
Each discovery costs days of elapsed time and a small, thinly spread effort
Tier-independent — it costs exactly the same in every enablement model
Squads' estimate: 30–40% of total elapsed time
Fix needs no re-organisation, no headcount, no integration
CAUSE 2 · STRUCTURAL FIX
Uniform allocation
Engagement depth does not vary with how much novel design an intake needs
8 of 38 scenarios need no design at all; 14 genuinely need a dedicated pod
All 38 currently receive the same dedicated team
In the absence of an objective rule, depth is allocated by influence
Fix needs a tiering rubric and the platform that makes lighter tiers safe
WHERE THE ELAPSED TIME ACTUALLY GOES
Mechanism
How it consumes time
Affects
Waiting for partner responses
Elapsed days per cycle, several cycles per phase
All three models
Re-explaining the same requirement
Every new participant needs the context rebuilt from scratch
All three models
Rework from assumed answers
Work proceeds on an assumption that later proves wrong
All three models
Discovery sessions that cannot conclude
The session runs without its input and has to reconvene
Lean+ and Dedicated
Follow-up loops at triage
Intake held in a waiting state with no enforced return date
All three models
Late-surfacing lead-time items
A long-lead request identified weeks after it could have started
All three models
Validating the 30–40% estimate costs almost nothing: count clarification cycles per intake and the elapsed days each consumed, across the last twelve months. That is a Sprint 1 deliverable, because the entire case for sequencing intake completeness first rests on it.
Notes: Set the frame for the technical audience: two causes, independent, different fixes. The equation is the structural statement. Both terms are outside our control today, so headcount is the only lever. Cause 1 is the one to spend time on with this audience, because they live it. The six-step cycle will be immediately recognisable. Make the point that it is tier-independent — no amount of re-tiering fixes it, which is why it goes first regardless of what leadership decides about the structural change. Cause 2 is the allocation problem. Be direct about the last bullet: in the absence of an objective routing rule, engagement depth gets allocated by influence. That is not an accusation, it is a structural observation, and the rubric exists to replace it. The bottom table is useful if anyone challenges the 30–40%. It decomposes where the time goes, so the estimate is defensible as a shape even before it is measured.

## Slide 3
2
The Intake Data Catalogue
54 data points across 10 categories — the asset the whole intervention rests on
Intake completeness
A
Business context and outcome
LOB ranking · UAT scope · RM obligation
5
B
Application and zone identity
Connectivity · certificates · access · subscriptions
6
C
Document inventory
Governance determination · profile design · capacity
8
D
Trust and classification inputs
Governance submission · DKE assessment
5
E
Retention and regulatory
Repository selection · RM questionnaire · tiering
6
F
Channel and integration
Ingestion design · reconciliation · event enablement
7
G
Metadata and retrieval
Profile configuration · search enablement
5
H
Security, access and users
Access provisioning · routing · certificates
4
I
Environments, testing, cutover
Promotion planning · UAT · release scheduling
4
J
Support and ownership
Handover · runbooks · BAU transition
4
WHAT EACH CATALOGUE ENTRY HOLDS
The question, in language a partner understands
Why it is required — the decision it feeds
What it blocks if absent, named as a specific gate
What a good answer looks like, with an example
Diagnostic sub-questions for a partner who does not know
Its completeness band
Which patterns make it applicable, so irrelevant questions are never asked
THE WHY-REGISTER IS THE ASSET, NOT THE CHATBOT
The conversational interface is the easy part. The valuable part is the register of reasons — the accumulated knowledge of why each item matters and what breaks without it. Roughly two weeks of two experienced engineers plus a governance analyst. Once written it serves the copilot, the partner documentation, squad induction and the pattern catalogue — it stops being one person's expertise and becomes the organisation's.
Applicability matters as much as coverage. The current workbook asks everyone everything, which trains partners to skim — and skimmed answers are the raw material of clarification cycles. The copilot derives which of the 54 apply from what the partner describes, then asks only those.
Notes: This is the slide architects should leave with a clear picture of, because it is the specification they will build from. Fifty-four data points. The counts per category are real and derived from walking the full lifecycle backwards from every gate: for each gate, what does it need, and where does that come from. The seven things each entry holds — point at the fifth one in particular. Diagnostic sub-questions are what turn "I don't know" from a dead end into a path. Most intake fields are blank not because the partner is unwilling but because they do not know and have no idea how to find out. The last one — applicability — is why this is not just a longer form. A partner consuming notifications only should never see a retention question. Asking everyone everything is what trains people to skim. On the two weeks: be specific that this is not a documentation exercise. It is capturing, for each item, the causal chain from the answer to the downstream configuration. That is why it needs experienced engineers and not a technical writer.

## Slide 4
3
How the Intake Copilot behaves
Four behaviours, each addressing one failure mode of the current workbook
Intake completeness
1
Derives the question set first
The partner describes the goal in their own words. The copilot determines which of the 54 points apply and in what order before asking anything.
2
Explains why, at the point of asking
Every question carries its reason — not as help text, but as part of the question, because a partner who knows what an answer is for gives a usable one.
3
Helps a partner who does not know
Offers realistic options with consequences, asks diagnostic sub-questions, surfaces contradictions, and registers a dated gap when the answer needs someone else.
4
Infers, and shows its working
Proposes what it can derive — trust pre-assessment, likely pattern, teams to engage, long-lead items — each labelled as an inference and correctable.
BEHAVIOUR 2 IN PRACTICE — THE SAME REQUIREMENT, ASKED TWO WAYS
Asked the current way
Asked with the reason attached
"What are the document traits?"
"Do any of these contain handwritten annotations or signatures? This decides whether they need human review after AI classification — typically two to three weeks and a separate engagement."
"What is your expected volume?"
"We need three numbers: initial migration, steady monthly rate, busiest expected day. The first drives one-time capacity; the third decides whether formal load testing applies."
"What are your retention requirements?"
"How long must these be kept, and what rule requires it? If it is regulatory rather than policy, the content goes to a different repository with immutable storage — not easily reversed."
BEHAVIOUR 3 IN PRACTICE — WHEN THE PARTNER DOES NOT KNOW
Partner says
Copilot does
"I don't know"
Offers the realistic options with their consequences — "most partners in your position are one of these three; here is how each changes your timeline"
"Not sure which applies"
Asks diagnostic sub-questions a non-specialist can answer, and derives the answer from those
Something inconsistent
Surfaces the contradiction immediately and asks which is correct, rather than recording both
"I need to ask someone"
Registers a dated gap with the owner named and the gate it blocks — this is the row that eliminates the discovery cycle
Notes: Walk the four behaviours, then spend the time on the two tables — they are what make the difference concrete. Behaviour 2: the right-hand column is the why-register doing its job. Note what changes — the partner is not being asked to understand the platform, they are being told the consequence of their answer. That is a question an application team can answer well. Behaviour 3, last row, is the economically important one. Converting "I need to ask someone" into a registered, dated, owned, gate-linked item is the mechanism that eliminates the discovery cycle entirely. The question still gets answered, but it is asked once, early, by the partner's own team, against a known deadline — instead of by us, late, under pressure. Behaviour 4 matters for the architects: every inference is labelled as an inference. Nothing the copilot proposes decides anything. That separation is on slide 9.

## Slide 5
4
Completeness bands and the handoff contract
Capture everything knowable now; convert the rest into scheduled-knowns
Intake completeness
FOUR COMPLETENESS BANDS, EACH MAPPED TO THE GATE IT BLOCKS
Mandatory to accept
Intake submission
IF UNANSWERED
Not accepted into the queue
TYPICAL CONTENT
Business outcome · application identity · zone · document types · named owners
Mandatory to design
P1 gate
IF UNANSWERED
Design baseline cannot close
TYPICAL CONTENT
Trust posture inputs · samples · retention obligation · volumes · channel
Mandatory to provision
P2 gate
IF UNANSWERED
Provisioning cannot complete
TYPICAL CONTENT
Metadata attributes · user populations · access routing inputs · certificates
Mandatory to certify
P4 gate
IF UNANSWERED
Promotion is blocked
TYPICAL CONTENT
UAT participants · cutover constraints · support model · escalation contacts
THE DISTINCTION THAT MAKES THIS WORK
A blank field and a field marked "not yet known — owner: partner solution architect — required by the design checkpoint on 14 November — blocks: repository profile design" are entirely different artefacts. The first is a future surprise. The second is a managed dependency with a name and a date against it.
THE HANDOFF CONTRACT — WHAT ARRIVES ON THE ECM BOARD WITH EVERY INTAKE
Validated answers
Every applicable point answered, validated at the point of capture
Registered gaps
Each with named owner, due date and the gate it blocks
Completeness score by band
Accept, design, provision and certify scored separately
Derived scope
Workstreams, specialist teams, approvals and their sequence
Long-lead items
Requests that should start immediately, with typical lead time
Pattern match and delta
Closest pattern, confidence, and what it does not cover
Proposed tier with reasoning
Seven determinant scores, for an enablement lead to confirm
Provisional assessments
Trust pre-assessment, load-test likelihood — labelled provisional
What this changes for the engineer: today they begin by working out what is missing — hours of effort, dependent on experience, and the start of the first clarification cycle. Under the contract they begin by reading a list of what is missing, who owns it and when it is due. The work does not disappear; it moves to the point in the lifecycle where it is cheapest.
Notes: The bands are the refinement that makes "capture everything at intake" actually achievable. Demanding every answer at intake is unrealistic and would just move the delay to the front door. A cutover window six months out genuinely is not knowable. So we band by the gate the item blocks, and anything not answerable now becomes a dated gap tied to that gate. Read the callout verbatim. It is the sentence that settles the objection "you cannot possibly get everything up front" — we are not claiming to. We are claiming nothing is ever discovered late. The handoff contract is the architects' interface. Whatever the intake tool ends up being, it must emit this package. Design to that contract and the rest of the platform can change underneath. The bottom note is the line to use with the squads. The work does not disappear — it moves to where it is cheapest. That is an honest framing and it lands better than claiming the work vanishes.

## Slide 6
5
The three enablement models
Same phases, same gates, same evidence — different distribution of the work
Operating model
LEAN
Self-service on a proven pattern
WHAT ECM PROVIDES
— Published, versioned pattern the partner instantiates
— Self-service provisioning within policy bounds
— Automated validation at every gate
— Generated artefacts, collections, documentation
— Bookable open clinic slots
— Automatic escalation on drift
WHAT THE PARTNER OWNS
— Completing intake to the published standard
— Implementing their side of the integration
— Running their own functional testing
— Clearing every automated gate
— Holding platform certification
Engagement is event-driven — no standing meetings, no allocated engineer
LEAN+
Shared pool with scheduled design assurance
WHAT ECM PROVIDES
— Everything in Lean, plus:
— A named enablement guide for the intake's life
— Two mandatory design reviews
— A standing weekly session, optional
— Shared-pool support for the novel elements
— Metadata mapping review, not delivery
WHAT THE PARTNER OWNS
— All Lean responsibilities
— First draft of design artefacts for review
— Driving implementation between checkpoints
Engagement is scheduled — the partner knows exactly when they get attention
DEDICATED
Allocated pod, inception to release
WHAT ECM PROVIDES
— An allocated cross-functional pod
— End-to-end ownership through stabilisation
— Authoring — not reviewing — design and mappings
— Continuous availability
— Direct coordination with specialist teams
WHAT THE PARTNER OWNS
— Requirements, samples and acceptance
— Business validation and sign-off
Engagement is continuous — the pod is the partner's delivery team
WHAT DOES NOT CHANGE ACROSS THE THREE MODELS — NO TIER CONFERS AN EXEMPTION
Classification determination
Retention approval
Security and access review
Volume certification
Promotion ladder
Support acceptance
Audit trail
New document type re-review
The argument to risk, audit and compliance is not that less rigour is applied in the lighter tiers. It is that the same rigour is applied by the platform rather than by an engineer's attention — which is more consistent, not less. A sampled proportion of completed Lean intakes is audited after go-live as the concrete assurance mechanism.
Notes: This is the model definition the squads will work to, so spend time on the "what the partner owns" rows — that is the part that changes behaviour. Lean: no standing meetings, no allocated engineer, no named delivery team. Interaction is event-driven. The partner's timeline is bounded by their own capacity, not by our queue. Lean+: the critical design point is that the guide is a contact, not a resource. A guide who starts doing the partner's implementation has converted a Lean+ intake into an unfunded Dedicated one. Guide time is tracked and capped for exactly that reason. Dedicated: retained deliberately and applied selectively. Note that it is the only tier where ECM authors rather than reviews. The invariant strip at the bottom is the compliance conversation. Walk it deliberately. Eight controls, identical in every tier, no exemptions. Then the note: the rigour is applied by the platform rather than by attention. That reframing is what gets the lighter tiers accepted.

## Slide 7
6
Tiering: how an intake is routed
Seven scored determinants, three thresholds, five hard overrides
Operating model
THE SEVEN DETERMINANTS — ABOUT THE WORK, NEVER THE REQUESTER
Determinant
Score 0
Score 1
Score 2
Score 3
D1
Pattern precedent and maturity
M3, exact fit
M3, tolerated variation
M1–M2 pattern
No pattern (M0 or none)
D2
Content trust posture
Unchanged, determined
New content, same posture
New posture for partner
Posture changing on live content
D3
Regulatory and records impact
None
Existing retention reused
New non-regulated retention
New regulated retention or WORM
D4
Classification engine change
None
Shadow or dry run only
Engine change, no new types
Engine change with new types
D5
Data model and metadata
No change
Additive, forward only
Structural, forward only
Historical content affected
D6
Volume and performance
Within current band
Band change, below threshold
Load testing triggered
Migration-scale or peak redesign
D7
Breadth of impact
Single partner, single flow
Single partner, many flows
Multiple business units
Multiple partners or dual-target
THRESHOLDS
0 – 5
Lean
A known pattern with known parameters. Nothing requires a decision not already made.
6 – 11
Lean+
A known pattern with one or two elements needing judgement. Review at the right moments suffices.
12 – 21
Dedicated
Genuine design work, or consequences severe enough that assurance must be continuous.
HARD OVERRIDES — FORCE A TIER REGARDLESS OF SCORE
Condition
Forces
Pattern maturity below M3
Not Lean
Pattern maturity below M1
Dedicated
Existing content or metadata remediated
Dedicated
or Factory
New regulated retention or WORM
Dedicated
Multiple LOBs or multiple partners
Dedicated
Tier is assigned by ECM against the published rubric and is never selected by the partner. If partners self-select, every partner selects Dedicated — not out of bad faith, but because from any one partner's view more attention is always better. Appeal is allowed once, within five working days, and must name which determinant is wrongly scored. Repeated successful appeals on the same determinant are a rubric defect, not partner gaming.
Notes: This is the mechanical heart of the model and the thing architects will stress-test. Invite them to. Each determinant is about the work. Deliberately absent: partner size, partner seniority, who asked loudest. In the absence of an objective rule those are what allocate depth today. D1 is the primary determinant and it is the one that moves over time. As patterns mature, intakes that scored 2 or 3 on D1 start scoring 0 or 1, and the whole distribution shifts leftward without any other change. The hard overrides exist because the score is a proxy for risk and in these five cases we know the risk directly. Two of them are maturity constraints rather than risk — you cannot do Lean without an M3 pattern because there is literally nothing for the partner to operate. The appeal mechanism matters for adoption. One appeal, five days, must name the determinant. And the calibration point: if the same determinant keeps getting successfully appealed, the rubric is wrong on that dimension — recalibrate rather than defend.

## Slide 8
7
The 38 scenarios, tiered
Entry distribution, the trajectory, and what drives each assessment
Operating model
DISTRIBUTION AT ENTRY AND AT STEADY STATE
At entry
Lean 8
Lean+ 14
Dedicated 14
2
Steady state
Lean 16
Lean+ 13
Ded 7
2
REPRESENTATIVE SCENARIOS AND WHAT DROVE THE ASSESSMENT
#
Scenario
Driving determinants
Tier
Condition / escalation
1
New Apigee subscription to call services
D1:0 · no posture or retention change
Lean
Escalates if the partner is not yet certified
9
Existing patterns, new content, same flows
D1:0 · D2:1
Lean
Escalates if a new type has no determination
5
Move from APIGEE-based to KAFKA-based ingestion
D1:1 · D6:1
Lean+
Dedicated if reconciliation semantics change
12
Existing partner and flows — data model update
D5:1–3
Lean+
Dedicated if historical content affected
22
New ingestions — untrusted and non-regulated
D2:2 · D4:2
Lean+
Dedicated if DKE coverage is thin
14
Untrusted content: legacy KOFAX to iDocs
D4:3 · D2:2
Dedicated
DKE coverage assessed before scoping
19
New ingestions — trusted and regulated
D3:3
Dedicated
Hard override — new regulated retention
25
New ingestions spanning multiple business units
D7:2
Dedicated
Hard override — multi-LOB
34
Making non-compliant systems or documents compliant
D2:3 · D5:3
Dedicated
Hard override — remediation of live content
30
RM remediation
D5:3
Factory
Dedicated if confined to one partner, novel scope
READ THE TRAJECTORY, NOT THE ENTRY FIGURE
Nine of the fourteen Lean+ scenarios move to Lean once their patterns reach M3. Four of the fourteen Dedicated scenarios move to Lean+ once delivered twice and harvested. Nothing migrates on its own — every leftward move is a pattern that a pod built and platform engineering hardened. This table is therefore also the platform backlog, prioritised: build first the patterns serving the highest-frequency scenarios currently sitting one tier too heavy.
Notes: Ten representative rows here; the full 38 are in Appendix A of the design document and should be circulated with this deck. The point to make with architects: the determinant column is the useful part. It shows exactly why each scenario landed where it did, which makes the assessment arguable on its merits rather than on authority. If someone thinks row 22 is wrong, they argue about D4, not about the conclusion. Note the three hard-override rows — 19, 25 and 34. Those did not need a score. We know the risk directly. Row 30 is the one that changes capacity most: records remediation leaves the onboarding queue entirely and becomes campaign work. That removes one of the most capacity-hungry scenario classes from pod contention. The band at the bottom is the planning instruction. The table is the platform backlog. Build the patterns that move high-frequency scenarios one tier lighter, in frequency order.

## Slide 9
8
Drift, escalation and certification
Novelty is not always visible at qualification — the model must handle that without a restart
Operating model
ESCALATION TRIGGERS — DETECTED AT ANY POINT, RE-TIER AUTOMATICALLY
Trigger
Escalates to
Why it cannot wait
A document type is introduced with no determination
Lean+
Governance must decide before any content configuration proceeds
DKE coverage gap identified for untrusted types
Dedicated
Classification accuracy cannot be configured around; the engine must be extended
Volume profile breaches the load-testing threshold
Lean+
Performance validation becomes a gating activity with its own lead time
Retention position changes to regulated
Dedicated
A regulated position must be authored and approved, not reviewed
Historical content comes into scope
Dedicated
Remediation of content under retention is a different risk class
Three consecutive failures on the same gate
Lean+
The partner is stuck and self-service is not resolving it — this is the design-help signal
Pattern variation falls outside declared tolerance
Lean+
The instantiated pattern no longer describes what is being built
A second line of business joins the scope
Dedicated
Coordination across owners cannot be delegated to a partner
RELEASING SCARCE CAPACITY
De-escalation
Downward movement is allowed but deliberate.
A Dedicated intake that completes its novel element and reverts to routine configuration may be de-tiered to Lean+ for the remainder, releasing the pod.
Taken at a phase gate, recorded with reason, never applied retroactively.
KEEPING TIERING ARGUABLE
Appeal
One appeal, to the enablement lead, within five working days of assignment.
Must identify which determinant is wrongly scored, and why.
Outcome recorded and fed into the quarterly rubric review.
Repeated success on the same determinant means the rubric is wrong — recalibrate.
A PARTNER EARNS LEAN
Certification — the gate on Lean
Platform onboarding completed by named contacts
At least one prior successful intake at Lean+ or Dedicated
A nominated technical owner, not a distribution list
Acceptance of the operating terms — no allocated capacity
Good standing: no unresolved compliance findings
Certification is held at partner level and persists, which means the first intake for any new partner is never Lean. That is deliberate: it gives ECM the opportunity to establish the relationship, and it guarantees a Dedicated or Lean+ delivery from which a pattern can be harvested.
Notes: Drift is the mechanism that makes it safe to tier early on imperfect information. The key design property: escalation carries everything already done. The partner does not restart. That is what allows us to tier optimistically at qualification rather than defensively. Row six — three consecutive failures on the same gate — is the one architects usually ask about. It is a deliberate circuit-breaker. A partner failing the same check three times is stuck, and self-service is demonstrably not going to resolve it. Escalating is cheaper than letting them grind. De-escalation is about pods, which are the scarcest resource. Once the novel element is done, release the pod and let the routine remainder run as Lean+. Without this, pods get held through phases that do not need them. Certification: the first intake for any partner is never Lean. Two reasons — they have not seen the process once with support, and we need a delivery to harvest a pattern from.

## Slide 10
9
Platform capability architecture
Five layers. Each independently useful, each a prerequisite for the one above.
Architecture
5
Partner cockpit and clinic
Where an intake is raised, state is visible, self-service actions are taken, clinic slots are booked and generated artefacts collected
4
Gate and policy engine
Evaluates whether an intake may advance, independently of who is asking. Deterministic, replayable, identical across tiers.
3
Provisioning engine
Turns a selected pattern plus a completed intake into actual configuration, within policy-approved bounds. Refuses rather than guesses.
2
Pattern catalogue
Versioned, executable descriptions of known onboarding shapes — steps, configuration, validations, tolerated variation
1
Enablement record
The durable record: scope, tier, every determination, every artefact, state across all phases, full audit trail
THE DEPENDENCY
What replaces the engineer in Lean
Knowledge of what to do next → pattern catalogue
Authority to provision → provisioning engine with policy bounds
Judgement that something is wrong → gate engine with explicit reasons
Memory of what was agreed → enablement record
Chasing and coordination → workflow and notification
Document production → artefact generation
SCOPE DISCIPLINE
What the platform deliberately does not do
Make content classification determinations
Decide retention positions
Replace architecture judgement on novel patterns
Grant approvals of any kind
Build the partner's own integration
Replace the enablement relationship in Dedicated
CHEAPER THAN IT LOOKS
Automate the decisions before automating the systems. A rule returning the correct answer — which project, which access path, whether this may promote — delivers most of an integration's value at a fraction of the cost, because the expensive part of integration is the connection, not the logic. Generation beats integration for the same reason.
Layer 1 is the layer that replaces one person's working memory, and everything above it depends on it being authoritative. Build it on existing tooling wherever possible — a new system of record is not required, and attempting one is how this becomes an eighteen-month programme.
BUILD SEQUENCE IMPLIED BY THE LAYERING
FIRST
Enablement record + intake capture
>
THEN
Pattern catalogue at M1
>
THEN
Gate engine + routing rules
>
THEN
Provisioning on one pattern
>
LAST
Cockpit and self-service
Notes: Five layers, bottom-up. Resist the temptation to start at layer 5 because it is the visible one. Layer 1, the enablement record, is the foundation and it is also the cheapest thing on this slide. It is a structured record — intake content, tier, determinations, gaps, artefact index, state, audit trail. Build it on what we already have. A new system of record is not required and attempting one turns this into an eighteen-month programme. The right-hand "what replaces the engineer" card is the architectural argument for why Lean needs all five layers. Removing the engineer without replacing their knowledge, their provisioning authority and their judgement is a service withdrawal, not a model. The "does not do" card is scope discipline. Every one of those is either a governance authority or genuine design work. Writing them down protects the build from expanding until it delivers nothing. The build sequence at the bottom is what sprints 1 to 4 implement.

## Slide 11
10
The pattern catalogue
The asset that decides whether any of this works
Architecture
WHAT A PATTERN CONTAINS
Identity and version
Stable identifier; intakes record which version they instantiated
Applicability
Channel, trust posture, regulatory status, content type, volume band
Step sequence
Ordered work with owner per step, split by who performs it in each tier
Configuration template
The platform configuration produced, parameterised against intake values
Required inputs
What the partner must supply, with a validation rule for each
Gate set
Which gates apply and the evidence each requires
Tolerated variation
Parameters that may differ without making the intake novel
Escalation triggers
Conditions that invalidate this pattern and force re-tiering
Generated artefacts
Documentation, collections and runbooks produced on completion
Precedent
Prior intakes using this pattern, with outcomes and known difficulties
MATURITY LADDER
M3
Self-service
Lean, Lean+
Fully provisionable by the partner within policy bounds
M2
Validated
Lean+
Automated gates; configuration generated, applied with review
M1
Described
Dedicated, Lean+
Generalised, required inputs defined
M0
Observed
Dedicated only
Delivered once; documented, not generalised
HOW PATTERNS ARE BORN — THE COMPOUNDING LOOP
STEP 1
Pod delivers a novel intake
Dedicated tier, end to end
>
STEP 2
Pod produces a pattern candidate
A closure condition, not a retrospective
>
STEP 3
Platform engineering hardens it
Generalise, validate, wire gates, build provisioning
>
STEP 4
Pattern enters catalogue at a maturity level
M1, M2 or M3
>
STEP 5
Matching intakes become eligible for lighter tiers
The distribution shifts
THIS IS THE ENGINE OF THE WHOLE MODEL
Dedicated work is not just delivery — it is pattern acquisition. A pod that delivers a partner successfully but produces no reusable pattern has done half its job, and the next identical intake stays just as expensive. That expectation must be built into how pods are measured, or the model quietly becomes a one-off efficiency exercise instead of a compounding one.
An intake can only be tiered to Lean if its pattern has reached M3. That gives the tiering rubric an objective constraint it cannot argue around, and it gives platform engineering an unambiguous backlog: move high-frequency patterns up the ladder, in frequency order.
Notes: The pattern catalogue is the single asset the model depends on. If this is weak, nothing above it works. Point at "tolerated variation" in the left-hand list. That field is what makes Lean safe — it declares exactly which parameters may differ between instances. Anything outside that boundary escalates automatically rather than being silently absorbed by a partner who does not know they have left the pattern. The maturity ladder is the gate on tier availability. M1 enables Lean+. M3 enables Lean. There is no judgement call here and there should not be — the pressure to open Lean early will be considerable because that is where the visible saving is. The five-step loop is the compounding mechanism. Step 2 is the one that will not happen unless we make it a closure condition. Architects and leads should hear this clearly: a Dedicated intake is not complete when the partner goes live, it is complete when the partner is live and a pattern candidate has been accepted by platform engineering.

## Slide 12
11
AI enablement and its guardrails
Separate proposal from decision from action — this is what makes AI acceptable here
Architecture
PROPOSE
AI assistance, grounded in the catalogue and record
DOES
Suggests a tier, a pattern, a scope, a mapping, a draft artefact, an answer to a question
MAY NEVER
Decide anything · write to a system of record · clear a gate
DECIDE
Deterministic rules — codified policy, not a model
DOES
Evaluates eligibility, completeness, routing, gate satisfaction, escalation triggers
MAY NEVER
Infer · approximate · give a different answer for the same input
ACT
Platform execution within policy bounds
DOES
Provisions configuration, raises requests, promotes environments, writes the audit trail
MAY NEVER
Act on a proposal that has not become a decision
AUTHORISE
Named humans, exactly as today
DOES
Governance determinations, records approvals, security approvals, go-live sign-off
MAY NEVER
Be delegated to any of the three layers above
THE TEN CAPABILITIES, ORDERED BY VALUE PER UNIT OF BUILD EFFORT
A
Intake Copilot
B
Pattern Matcher
C
Tiering Assistant
D
Scope Derivation
E
Artefact Generator
F
Gate Engine
G
Onboarding Assistant
H
Drift Detector
I
Precedent Retrieval
J
Clinic Triage
The first four carry most of the benefit and none requires deep integration. · F is explicitly not AI — gates are codified policy, replayable and explainable by pointing at a rule.
AI-SPECIFIC GUARDRAILS
No AI output is a gate decision
Every output grounded and cited
Confidence thresholds, with refusal below them
Human acceptance before any write to a system of record
No AI determination of classification, retention or security posture
Proposal and acceptance both recorded
Partner-facing assistant has no write access
Spot-audit of AI-assisted intakes
Read the four-layer table to a compliance audience and the conversation changes. Their concern with AI in a regulated content platform is never that it drafts a document — it is that it decides something consequential and nobody can reconstruct why. Here AI never decides, a deterministic rule does, a human authorises anything with consequence, and every step is recorded.
Notes: This slide is the one to use in any conversation with risk, compliance or audit. The four-layer separation is the architectural rule everything else depends on. Walk it slowly. AI proposes. Deterministic rules decide. The platform acts, only on decisions. Humans authorise anything consequential. The "may never" column is as important as the "does" column. In particular: AI may never clear a gate, and the gate engine is explicitly not AI. Gates are codified policy — same inputs, same outcome, every time, explainable by pointing at a rule rather than at a model's reasoning. The ten capabilities are ordered by value per unit of build effort, not by sophistication. A to D carry most of the benefit and none of them needs deep integration into downstream systems. That ordering is what makes the four-sprint plan credible. The guardrail strip: the fifth one is the line that matters most here — no AI determination of classification, retention or security posture, ever. Those are governance, records and security authorities and nothing in this architecture touches them.

## Slide 13
12
The phase model
Six phases, same gates in every tier — only who does the work changes
Operating model
Phase
Gate
Lean
Lean+
Dedicated
P0 Qualify
Qualified
Automated match; platform confirms tier
Automated match; lead confirms; guide assigned
Lead determines; pod assigned or queued
P1 Design
Design baselined
Pattern is the design — determinations pre-made
Partner drafts; guide reviews at checkpoint 1
Pod authors with partner, governance and RM
P2 Provision
Provisioned
Partner self-serves within policy bounds
Partner self-serves; ECM handles exceptions
ECM provisions on the partner's behalf
P3 Build
Integration complete
Unsupported, pattern-guided; clinic if blocked
Weekly optional session; guide brokers
Joint working; pod brokers directly
P4 Validate
Certified
Generated test plans; partner executes
Guide reviews scope at checkpoint 2
Pod authors plans and works alongside
P5 Release
Live and supported
Standard handover; straight to BAU
Guide on call; two weeks availability
Pod present; four weeks stabilisation
ONE ROW IS IDENTICAL IN ALL THREE COLUMNS
Promotion is a platform action in every tier, never a human one. A Lean intake is not progressing on a lower standard — it is progressing on exactly the same standard, evaluated by the same engine. That uniformity is the entire compliance defence for the lighter tiers.
WHERE EACH PHASE IS HEAVIEST, AND WHY
P0 Light in every tier
The work is routing, not delivery
P1 Heaviest in Dedicated, near-zero in Lean
In Lean the determinations were made when the pattern was built
P2 Highest automation yield of any phase
Almost entirely rule-application and request-routing
P3 Smallest ECM role in every tier
The work is substantially the partner's own development
P4 Gate density is highest; identical across tiers
Evidence requirements do not vary by tier
P5 Largely generation plus a small human core
Transition page and runbooks generate; release night does not
P2 deserves particular attention in the build plan. Almost everything in it is rule-application and request routing — the work that consumes the most engineer attention for the least design value, and where misrouting fails silently rather than loudly. It is the highest-yield automation target in the entire lifecycle.
Notes: This is the operating model the squads will run. The important message is that the phases and gates do not change — only the distribution of work. P1 is where the model earns or loses credibility. Every expensive failure in onboarding traces to a determination made late or assumed. In Lean these are not skipped — they were made once, when the pattern was built, and the pattern only applies to content where they still hold. That is the precise mechanism by which Lean is fast without being reckless, and it is worth saying out loud to anyone who suspects the lighter tier cuts corners. P2 is the automation prize. Rule-application and routing. Note that misrouting fails silently today — a ticket in the wrong project is not rejected, it is simply invisible to the team that needs to action it. The band in the middle is the compliance line. Promotion is a platform action in every tier. No human promotion path anywhere.

## Slide 14
13
Guardrails
What makes the lighter tiers defensible — and what keeps the model itself healthy
Guardrails
UNIVERSAL — ALL TIERS, NO EXCEPTIONS
Guardrail
What it enforces
How
Classification determination
No content configured against an asserted posture or classification
Gate engine blocks P1 exit; provisioning refuses without a registered determination
Retention approval
No retention configured without RM approval against a stated obligation
Gate engine blocks P2 exit; never a self-service action in any tier
Security and access
Routing follows published rules; production access needs approval
Platform resolves routing and refuses rather than guessing
Promotion ladder
No environment skipped, no gate bypassed
Promotion is a platform action, never a human one
New document type
A later type does not inherit an existing classification
Detected automatically; forces escalation and a fresh determination
Audit trail
Every action, approval and promotion is attributable
Written at the point of action; not reconstructable afterwards
TIER-SPECIFIC
LEAN
— Certification prerequisite — first intake is never Lean
— M3 pattern required
— Tolerated variation explicit and narrow
— Three-strike escalation on repeated gate failure
— No silent exceptions — refuse rather than guess
— Compliance spot-audit after go-live
— Clinic access guaranteed, not optional
LEAN+
— Both checkpoints mandatory — never waived or combined
— Checkpoints require a completed artefact; no artefact, no review
— The guide is a contact, not a resource — time tracked and capped
— Escalation is automatic, never negotiated
DEDICATED
— Pattern harvest is a closure condition
— De-escalation at phase gates releases the pod
— Tier justification recorded against the intake
— Queue position disclosed to the partner
GUARDRAILS ON THE MODEL ITSELF — THE MODEL CAN FAIL WITHOUT ANY INDIVIDUAL INTAKE FAILING
Signal
Threshold
Intervention
Escalation rate out of Lean
Above 20%
Pattern mis-scoped or rubric mis-calibrated — suspend Lean for that pattern and re-harden
Pattern debt
Dedicated closing without a candidate
The compounding has stopped — treat as a delivery defect, not an administrative gap
Platform team raided for intake work
Any occurrence
Escalate to leadership immediately — this is the failure mode that ends the programme
Notes: Guardrails are the reason the lighter tiers survive contact with risk and audit. Walk the universal set first and make the point that none of them is waivable by any tier. The tier-specific ones are where the squads need to be disciplined. Two in particular: Lean+, third bullet: the guide is a contact, not a resource. A guide who starts doing implementation has converted a Lean+ intake into an unfunded Dedicated one using capacity that was never allocated. This is the most likely way the model quietly fails, and it happens with the best intentions. Dedicated, first bullet: pattern harvest as a closure condition. Without it the model stops compounding. The bottom table is the part leads should own. The model can fail without any single intake failing — escalation rate creeping up, pattern debt accumulating, the platform team being borrowed for a pressured quarter. That last one is always justified at the time and it is the single fastest way to end the programme. Say so explicitly and get leadership to commit to protecting it. And the response protocol: a guardrail that fires and is then worked around is worse than no guardrail, because it teaches everyone the controls are advisory. Blocked, not warned. Reason returned in full. Routed to who can resolve it. Written to the audit trail. Override only by the named authority, and the override is itself audited.

## Slide 15
14
Team structure
Five functions replacing three undifferentiated scrum teams
Organisation
Platform Engineering
9
Build the platform and move patterns up the maturity ladder. Takes no intakes.
MEASURED BY
Pattern maturity progression; share of intakes eligible for Lean
Enablement Pods
10
Deliver Dedicated intakes end to end and harvest a pattern at closure.
MEASURED BY
Delivery outcomes and pattern candidates produced
Enablement Clinic
7
Scheduled design assurance for Lean+; on-demand unblocking for Lean.
MEASURED BY
Checkpoint coverage; time-to-unblock; escalation rate
Migration Factory
4
Run legacy and non-compliant remediation as campaigns, not onboardings.
MEASURED BY
Content volume remediated; repositories decommissioned
Governance & Compliance Desk
3
Hold the determinations every tier depends on, to a published service level.
MEASURED BY
Determination turnaround; compliance findings avoided
THE DIAGNOSIS
Why the current shape cannot deliver it
Everything competes with everything — routine work fragments complex work in one backlog
Nobody owns the platform, which is why patterns are not harvested today
Specialist governance knowledge is spread thinly across three teams at partial depth
HEADCOUNT — 33 TODAY, 33 TARGET
Function
Today
Target
Platform Engineering
0
9
Enablement Pods
0
10
Enablement Clinic
0
7
Migration Factory
0
4
Governance Desk
0
3
Current scrum teams
33
—
TRANSITION SEQUENCING — STRUCTURAL CHANGE FOLLOWS EVIDENCE, IT DOES NOT PRECEDE IT
WAVE 0 · MONTHS 0–3
Desk + platform seed
Rubric published · record and cockpit v1 · no tier changes to in-flight intakes · no Lean
>
WAVE 1 · MONTHS 3–9
Clinic opens, Lean+ live
Platform to full size · three M1–M2 patterns · harvest becomes a closure condition · Lean stays closed
>
WAVE 2 · MONTHS 9–18
Lean opens, pods formalised
First M3 patterns · certification live · Migration Factory stands up
>
WAVE 3 · MONTHS 18+
Coverage broadens
Distribution shifts toward Lean · factory runs continuous campaigns
The sequencing rule that must not be broken: a tier opens for a pattern only when that pattern's maturity supports it. Lean+ needs M1, Lean needs M3. Pattern maturity, not elapsed time, is the gate on tier availability — and the pressure to open Lean early, before patterns are ready, will be considerable.
Notes: Be straightforward with this audience about what the re-organisation means for them, because they will work it out anyway. The total does not change. This is a redistribution, not a headcount reduction proposal. The benefit is absorbing more intake volume with the same people. Platform Engineering is funded from delivery capacity. Nine engineers move from delivering intakes to building the capability that reduces the cost of intakes. Throughput dips before it rises — say so. The role shifts are real and not everyone will want all of them. Moving from delivery to product trades visible partner outcomes for capability that pays off later. Clinic engineers review work they would previously have performed, which is a genuinely different skill — faster, more judgement-dense, less hands-on. Factory engineers work in volume and repetition rather than relationships. Give people a route to the role that suits them rather than assigning by availability. Pattern Engineer has no current equivalent and is the hardest role to fill internally. The wave sequencing is deliberately slow at the front. Wave 0 changes nothing structurally — it publishes the rubric and stands up the record. That is on purpose: structural change follows evidence.

## Slide 16
15
The game plan — sprints 1 and 2
Eight weeks, five to six people, no structural change
Game plan
THE TEAM
1.0
Product owner / enablement lead
Rubric, tiering decisions, partner and squad adoption, backlog
2.0
Platform engineers
Enablement record, rules engine, generation, cockpit
1.0
Pattern and content analyst
Intake data catalogue and why-register, pattern documentation
0.5
Governance and records analyst
Why-register entries for classification and retention, gate definitions
1.0
Enablement engineer (clinic pilot)
From sprint 3 — runs the first checkpoints and clinic slots
SPRINT 1 · WEEKS 1–2
Complete the intake
Goal: from day one, every new intake is captured completely, with the reason for each requirement explained at the point of asking, and every remaining unknown registered as a dated, owned, gate-linked gap.
Intake Data Catalogue and why-register
All 54 points with reason, blocker, good answer, diagnostics, band
Intake Copilot v1
Applicability filtering, reasons attached, assistance, inference with working shown
Completeness validation and banding
Deterministic scoring against accept / design / provision / certify
Gap register
Named owner, due date, blocking gate — converts discovery into scheduling
Handoff contract
The completeness certificate accompanying every intake onto the board
Long-lead item flagging
Connectivity, certificates, specialist engagements surfaced on day one
Clarification-cycle baseline
Count and elapsed days across 12 months — measures the 30–40%
Rubric published + retrospective scoring
Parallel, low effort — tests the structural assumption
SPRINT 2 · WEEKS 3–4
Make intake drive everything downstream
Goal: the content captured in Sprint 1 starts producing scope, tier, pattern and precedent automatically, so an engineer picking up an intake begins with analysis rather than assembly.
Scope derivation v1
Workstreams, specialist teams, approvals and their sequence
Tiering Assistant
Seven determinants scored with visible reasoning; lead confirms
Pattern Matcher v1
Match against documented patterns and scored history; returns the delta
Precedent Retrieval
Comparable prior intakes, decisions and known difficulties
Top three patterns to M1
Highest-frequency scenarios from the retrospective scoring
Dual-run tiering begins
Tiered and recorded, still delivered under the current model
Enablement record v0
Thin structured record, built on existing tooling where possible
Phase baseline measurement
Effort and elapsed time against the six phases
Exit criteria — Sprint 1: catalogue published; three partners complete an intake through the copilot with no engineer involvement; every new intake arrives with a completeness certificate; clarification cycles measurably below baseline. · Sprint 2: scope and tier derived automatically; three patterns at M1; an engineer picking up an intake receives a derived scope and a proposed tier.
Notes: This is the sprint-level plan the leads will run. Five to six people. A tiger team, not the organisation. Existing teams keep delivering throughout — that is deliberate and it is what makes this a low-risk ask. Sprint 1 is intake completeness and the catalogue is the critical path item. It is roughly two weeks of two experienced engineers and the governance analyst. If that slips, everything slips, so protect it. Note that the rubric publication and retrospective scoring run in parallel as low-effort items. They are not the sprint goal — they are two days of analyst work that happen alongside, and they produce the evidence leadership needs for the structural decision. Sprint 2 is where the intake content starts earning its keep. Everything here consumes what sprint 1 captured, which is exactly why the sequencing is this way round. A tiering assistant scoring a vague intake produces a vague tier. Dual-run tiering is worth calling out: we assign and record a tier for every new intake but still deliver it under the current model. Real data, zero risk, and it gives us the distribution evidence without committing to anything.

## Slide 17
16
The game plan — sprints 3 and 4
Guardrails, the Clinic, and proving Lean end to end
Game plan
SPRINT 3 · WEEKS 5–6
Guardrails, generation, and the Clinic opens
Goal: Lean+ becomes a real tier with real intakes running through it.
Gate engine for P0 and P1
Deterministic evaluation with itemised failure reasons
Routing rules codified
Ticket routing, access path, environment account mapping
Artefact Generator v1
RM questionnaire draft, scope summary, test plan, API collection
Partner Onboarding Assistant
Grounded answers with citation and refusal behaviour
Clinic stands up
Checkpoint calendar, open slots, escalation duty, triage front door
Three patterns to M2
Automated gates; configuration generated and applied with review
First Lean+ intakes
Three to five, with real checkpoints and a named guide
Enabling squad onboarding
Tiering model, clinic rhythm, new roles — run with them, not at them
SPRINT 4 · WEEKS 7–8
Prove Lean on one pattern
Goal: at least one partner completes an intake end to end with no allocated ECM capacity.
Self-service provisioning, one pattern
Highest-frequency pattern only — likely subscription extension
That pattern promoted to M3
Provisioning, gates, artefacts, declared tolerated variation
Partner certification live
Criteria published; two to three partners certified
Cockpit v1
State, gate status, blocked items with owners and age, next action
Drift Detector v1
Escalation triggers evaluated automatically
Leadership dashboard v1
Distribution, dwell time, escalation rate, gate failure, clinic demand
First Lean intake completed
One partner, end to end, no allocated capacity
Adoption push
Wider partner comms; squads on the new rhythm; in-flight intakes left alone
DELIBERATELY NOT ATTEMPTED IN FOUR SPRINTS — SCOPE DISCIPLINE
Deep integration with every downstream system
Generation and rules deliver most of the value first
All 38 patterns
Three cover a disproportionate share of volume
A full partner portal
The cockpit is a state view, not a product
Retiring any existing tooling
Nothing is switched off in eight weeks
Migrating in-flight intakes
Partners mid-delivery are left alone
The Migration Factory
Important, but separable — starts after onboarding is proven
Full team re-organisation
Five or six people prove the model first
Headcount commitments
No capacity claim until the baseline exists
Adoption: choose the first three partners deliberately — one high-frequency simple partner who will succeed quickly and generate a reference, one mid-complexity partner who genuinely exercises Lean+, and one known sceptic, because a model that only works with enthusiasts does not work. Never force a tier change on an in-flight intake; that is how the model acquires its first horror story.
Notes: Sprint 3 makes Lean+ real. The clinic rhythm is the part that needs the squads involved in designing, not just told about — they are the people whose working week changes most. Sprint 4 proves Lean on exactly one pattern. Not three, not five. One. The highest-frequency one, most likely subscription extension. One partner live end to end with no allocated capacity is a far stronger proof point than three patterns half-built. The "not attempted" grid is the most important thing on this slide for a technical audience, because the pressure to expand scope will come from people who mean well. Deep integration in particular — it looks like the obvious thing to build and it is the thing that turns eight weeks into eight months. Adoption: the sceptic partner is a deliberate choice. If the model only works with enthusiastic partners, it does not work. Better to find out in sprint 4 with a controlled pilot than in month nine at scale. And the rule about in-flight intakes — leave them alone. Forcing a model change on a partner mid-delivery is how we acquire the story that follows this programme around for two years.

## Slide 18
17
Measures, risks and what good looks like
How we will know this is working — and the three ways it fails
Closing
THE SCORECARD — EIGHT MEASURES, ALL AVAILABLE FROM THE PLATFORM RATHER THAN ASSEMBLED BY HAND
Measure
Why it is on the list
After 4 sprints
At 12 months
Clarification cycles per intake
The largest single source of delay
Baselined; lower on pilots
Near zero on mature patterns
Intake completeness at handoff
Whether the data deficit is closing at source
Certificate on every intake
90%+ answered or dated
Tier distribution
Whether pattern investment is working
Known and baselined
40%+ Lean or Lean+
Intakes absorbed per period
The capacity outcome leadership is buying
Baseline established
Rising at constant headcount
Intake-to-live elapsed time by tier
Partner-visible value
First Lean comparison
Lean materially below Dedicated
Pattern maturity progression
Leading indicator of future distribution
Three at M2, one at M3
Twelve-plus at M2 or above
Pattern candidates per Dedicated closure
Whether the compounding works
Process defined
One per closure, no exceptions
Compliance findings on completed intakes
Whether lighter tiers are safe
No regression
No increase on baseline
THE THREE WAYS THIS FAILS
Platform team is raided for delivery work
Always justified at the time. Once it happens the function never recovers, because the platform never reaches the maturity that would have relieved the pressure.
MITIGATION Explicit leadership protection; monitored as a guardrail; escalate on any occurrence
Lean opens before patterns are mature
Produces unsupported partners, failed onboardings and a permanent credibility loss. The pressure will be considerable — it is where the visible saving is.
MITIGATION Pattern maturity is a hard constraint, not a guideline. M3 required for Lean.
Patterns are not harvested
The compounding stops and the model quietly becomes a one-off efficiency exercise rather than a capability that grows.
MITIGATION Closure condition on Dedicated intakes; monitored as pattern debt
THE THREE QUESTIONS TO ASK AT EVERY CHECKPOINT
1 — Is the tier distribution moving, and is the movement explained by pattern maturity rather than by softer assignment? 2 — Are Dedicated intakes producing pattern candidates? 3 — Has the platform team been pulled into delivery work?
Notes: Close on measures and failure modes rather than on benefits — this audience will respect that more, and they are the people who will see the failure modes first. The scorecard is deliberately short. Eight measures, all produced by the platform rather than assembled by hand, which is itself part of the point — the measurement infrastructure does not exist today and that is why nobody can currently answer how long onboarding takes. The first two measures are the ones that move in the first eight weeks. The rest are twelve-month measures. On the three failure modes: all three are quiet failures. None of them produces an incident. The platform team gets borrowed for a pressured quarter and it is entirely reasonable at the time. Lean opens a pattern early because a partner is waiting and it seems harmless. A pod closes without a pattern candidate because the partner went live and everyone moved on. That is why the three checkpoint questions matter. They are specifically designed to catch quiet failures, and leads should ask them of themselves at every sprint boundary, not wait for leadership to ask. Last thing to leave them with: this design asks a lot of the squads in terms of role change, and the honest version is that not everyone will want every role. Give people a route to the one that suits them — pod, clinic, platform or factory — rather than assigning by who happens to be available.